## Sheet1
Step | Description | Estimated Time (Weeks) | Target Date | Responsible Parties | Comments
1 | Prepare and issue RFI to list of vendors previously provided by FM. | 3 | 2014-08-15 | UIUC, PEI, FM | Includes indicative pricing, standard terms, sample PPA, ownership structure and other critical contractual terms. Includes time to determine operational needs and constraints.
2 | Responses to RFI due to PEI. | 2 | 2014-08-29 | UIUC, PEI, FM
3 | Review RFI responses. | 9 | 2014-10-31 | UIUC, PEI, FM | Includes indicative pricing, standard terms, sample PPA, ownership structure, critical contractual terms and credit-worthiness.
4 | Issue RFP based on results of RFI. | 3 | 2014-11-21 | UIUC, PEI, FM | Focused list of vendors based on results of RFI.
5 | Responses to RFP due to PEI. | 3 | 2014-12-12 | UIUC, PEI, FM
6 | Review RFP responses, including standard PPA’s, credit worthiness, ownership structure and other terms. | 6 | 2015-01-23 | UIUC, PEI, FM
7 | Notification of award. | 1 | 2015-01-30 | PEI
8 | Negotiate and execute PPA with winning bidder. | 13 | 2015-04-30 | UIUC, PEI, FM
9 | Delivery begins. |  | 2015-07-01
| Total Time Estimate (weeks) | 40
UIUC = University of Illinois at Urbana-Champaign
PEI = Prairieland Energy, Inc.
FM = Fellon McCord