## Tier 1
Tier 1
Equipment & Construction Costs |  |  |  |  | Task | Timeframe (# of weeks to completion) | Estimated Completion Date
Biodiesel Engine |  | 450 | 2 | 900 | Convert Diesel Engine | 3 | 2014-09-26
Biodiesel Processor |  | 1500 | 1 | 1500 | Main Wing | 4 | 2014-10-03
Carbon Fiber Mold |  | 600 | 1 | 600 | Install Engine | 3 | 2014-10-17
Carbon Fiber Cloth |  | 50 | 2 | 100 | Fuselage | 4 | 1900-10-31
Composite Resin |  | 30 | 2 | 60 | Tail | 2 | 2014-11-07
Carbon Fiber Plates |  | 100 | 4 | 400 | Avionics | 8 | 2014-10-31
Carbon Fiber Spars |  | 50 | 1 | 50 | Complete Assembly | 4 | 2014-12-05
Avionics Hardware |  | 500 | 1 | 500 | Testing | 2 | 2014-12-15
Composite Skin |  | 200 | 3 | 600
0
|  |  | Subtotal | 4710
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
Personnel & Wages
Machine Shop |  | 60 | 4 | 240
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 240
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
|  |  | TOTAL BUDGET | 4950

## Tier 2
Tier 2
Equipment & Construction Costs |  |  |  |  | Task | Timeframe (# of weeks to completion) | Estimated Completion Date
Airframe |  | 20000 | 1 | 20000 | Start up (Training/Preparations) | 8 | 2015-03-16
Engine |  | 15000 | 1 | 15000 | Canard | 4 | 2015-04-13
Avionics |  | 12980 | 1 | 12980 | Canopy | 4 | 2015-05-11
[5 empty] | Centerspar | 2 | 2015-09-07
[5 empty] | Fuselage | 5 | 2015-10-12
[5 empty] | Nose | 3 | 2015-11-02
[5 empty] | Roll Trim | 3 | 2016-02-08
[5 empty] | Landing Gear | 3 | 2016-02-29
[5 empty] | Wings | 5 | 2016-04-04
|  |  |  | 0 | Final Integration | 5 | 2016-05-16
|  |  | Subtotal | 47980 | FAA Approval | 3 | 2016-07-04
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
|  |  | TOTAL BUDGET | 47980