## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Restoration of Low Mow Area at Orchard Downs Housing Faculity
Total Amount Requested from SSC: | 8000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Start Date | 209 |  | 2023-08-01
Seed Collection | 3 |  | 2019-10-27
Inventory of plants | 2 |  | 2019-10-20
Removing unwanted species | 4 |  | 2019-11-03
Growing Plants in the Greenhouse | 30 |  | 2020-04-30
Plant plugs | 35 |  | 2020-06-04
Repeat Process for 1 to 2 years
Survey plot to see which species are growing | 209 |  | 2023-08-01
Final Report | 209 |  | 2023-08-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs |  |  |  | Notes
Water | 7.1 | 6 | 42.6 | estimate of $7.10 per 1,000 gallons
0
0
0
0
0
0
0
0
0
|  | Subtotal | 42.6
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
Mowing 1 time per year | 0 | 4 | 0 | Facility and Services will do this for free once a year
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Greenhouse space | 1000 | 3 | 3000 | Estimation based on 2 (5 ft by 4ft) = $500 per semester
Native plant seeds/ plugs | 700 | 2 | 1400
Garden Trowel | 6 | 15 | 90
Hand Weeder | 6 | 10 | 60
Land Augur Drill Bit and Cordless Drill | 45 | 1 | 45
Herbicide (Chemicals, spray backpack, mixing tools) | 200 | 1 | 200
Truck Rental for moving plants | 30 | 1 | 30
Yard bags | 4 | 5 | 20
Yard Plaque or Large Engraved Rock | 100 | 1 | 100
Money for unknown misc. items/ possible problems (die off of plants, miscalculation of prices, community events for the plot) | 3000 | 1 | 3000
|  | Subtotal | 7945
|  | TOTAL BUDGET | 7987.6
End of Application