## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Engineering Assessment of HVAC Indoor Air Quality Performance Verification for Energy Efficient Infection Control
Total Amount Requested from SSC: | 11488
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Test Site Floor Plan Analysis, Determine Test Site Design |  |  | Completed Thurs Nov 18, 2021
Develop Project Protocols, Establish Sampling Methods |  |  | (required for proposal testing protocol and budget)
Identify Sampling Points, Origin Points + Test Intervals | 2-weeks
Materials Procurement, On-site Delivery and QC | 1-week
Set-up, Testing and Chain of Custody Implementation | 1-day |  | TBD (Full Saturday Jan 2022)
Lab Testing and Results | 10-days |  | Within 10-days following Jan 2022 test date
Final Report Writing and Quality Control | 1-week |  | One week after reciept of lab results
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Spray Nebulizer DNA w/Tag Label TAGGING SYSTEM | 199 | 16 | 3184
Air Sample Pumps With Batteries AIR SAMPLES | 110 | 20 | 2200
Extra AAA Batteries 20-ct (3 each pump) ENERGY | 24.5 | 2 | 49
Filters (Box) LAB MATERIAL | 70 | 1 | 70
Cassettes + Filters LAB MATERIAL | 25 | 16 | 400
Cassette Plugs (Red) Bottoms (BLUE) LAB MATERIAL | 10 | 16 | 160
Ziplock Sample Bags (Large) LAB MATERIAL | 20 | 1 | 20
Plastic Weigh Boat LAB MATERIAL | 25 | 1 | 25
Cotton Swab 100-ct LAB MATERIAL | 15 | 1 | 15
Clean Floor Plans (on paper) PRINTED MATERIALS | 2 | 1 | 2
Annotated Plans (on paper) PRINTED MATERIALS | 2 | 1 | 2
Data Collection Form PRINTED MATERIALS | 2 | 1 | 2
Materials and Equipment Checklist PRINTED MATERIALS | 2 | 1 | 2
QC Checklist PRINTED MATERIALS | 2 | 1 | 2
Chain of Custody Form PRINTED MATERIALS | 2 | 1 | 2
Origin Point Labels PRINTED MATERIALS | 10 | 1 | 10
Sample Number Labels PRINTED MATERIALS | 20 | 1 | 20
Extra Set Of OP/SP/SN Labels PRINTED MATERIALS | 20 | 1 | 20
Face Masks SAFETY PPE | 30 | 1 | 30
Lab Test Results | 1050 | 1 | 1050
|  | Subtotal | 7265
Publicity & Communication
Ongoing Indoor Air Quality Data Monitor | 399 | 1 | 399
w/App and Cloud-Connected Dashboard |  |  | 0
0
0
0
0
0
0
0
0
|  | Subtotal | 399
Personnel & Wages
Dhruvaraj Gambhire - Candidate M Eng Energy Systems | 15.5 | 58 | 899
Ali Khan - Candidate M Eng Energy Systems | 15.5 | 58 | 899
0
Sterling Laylock - Sustainable Dev Director (-100% hr/rate) | 0 | 18 | 0
Michael Sheehan - Project Manager (-50% hr/rate) | 87.5 | 20 | 1750
Crystal Brooks - Quality Control and Information (-50% hr/rate) | 37.5 | 5 | 187.5
0
0
0
0
|  | Subtotal | 3735.5
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Sharpies (Box-12) OFFICE SUPPLIES | 26.5 | 1 | 26.5
Pens OFFICE SUPPLIES | 15 | 1 | 15
Post-it-Notes OFFICE SUPPLIES | 10 | 1 | 10
Clipboards OFFICE SUPPLIES | 2 | 6 | 12
Clean Gloves Large (Box 100) CLEANING SUPPLIES | 10 | 1 | 10
Chlorine Bleach Wipes CLEANING SUPPLIES | 15 | 1 | 15
0
0
0
0
|  | Subtotal | 88.5
|  | TOTAL BUDGET | 11488
End of Application