## Sheet1
Topic | Comment | From | Response/Action
Maintenance | Previous agreements from original MOA still apply. “University grants to the Donor a temporary, non-exclusive access license and the authority to work on University property…”. “Future maintenance costs at or below current practices will be supported by Facilities and Services.” “At the request of Facilities and Services, the SSC agrees to cover the cost of restoring the location to grass should the project be unsuccessful.”(after 5 years). | MAE | This was already understood.
parking | Who would regulate parking? Metered spaces? | MAE | MBJ emailed Tom at Parking 7/12/11 to confirm that the Parking Department would install and enforce these spaces
viewing platform | The wood ramp and viewing platform need to be designed and constructed by professionals. | MAE | This was already understood.
viewing platform | I agree strongly with Matt, that any platform design and construction will require professional services and must be fully accessible. | CPG | This was already understood.
path layout | Are six foot wide mown pathways acceptable Craig? | MAE | See CPG comments for response
path layout | Should a pathway connection from the southeast corner to the northwest corner be included? | MAE
path layout | Should an internal access path to the circular formal garden be included? | MAE
path layout | As for the site access, I would suggest that the beginning public access route from the south side of the site provide a path from the parking spaces to the point of entry to the prairie with a ‘firm and stable surface” to meet the criteria of the ADA for accessible routes. | CPG
path layout | I would also suggest that the paths through the prairie site be evaluated for the potential to provide accessible routes with the correct slope and width. If it turns out that it is impractical to provide an accessible route through the prairie site to the rest and info stations, we may be able to provide “equivalent facilitation” by placing an information station that shows the plant species, information conveyed at the stations, etc. | CPG
path layout | My only question would be if a path to the east and west be added to criss cross the space and add several access routes for visitors to use. Having to walk all the way to the north or south end seems a little limiting once you are out in the middle of the space. Just a thought. | BAF