## Sheet1
Step | Description | Estimated Time (Weeks) | Target Date | Revised Target Date | Responsible Parties | Comments | Status
1 | Prepare and issue RFI to list of vendors previously provided by FM. | 3 | 2014-08-15 | 2014-08-15 | UIUC, PEI, FM | Includes indicative pricing, standard terms, sample PPA, ownership structure and other critical contractual terms. Includes time to determine operational needs and constraints. | þ
2 | Responses to RFI due to PEI. | 2 | 2014-08-29 | 2014-09-05 | UIUC, PEI, FM | Revised date due to vendor request for additional time to prepare response.
3 | Review RFI responses. | 9 | 2014-10-31 | 2014-11-06 | UIUC, PEI, FM | Includes indicative pricing, standard terms, sample PPA, ownership structure, critical contractual terms and credit-worthiness. Delayed target reflecting longer RFI response time.
4 | Issue RFP based on results of RFI. | 3 | 2014-11-21 | 2014-11-25 | UIUC, PEI, FM | Focused list of vendors based on results of RFI. Delayed target reflecting longer RFI response time. Delayed target reflecting longer RFI response time.
5 | Responses to RFP due to PEI. | 3 | 2014-12-12 | 2014-12-16 | UIUC, PEI, FM | Delayed target reflecting longer RFI response time.
6 | Review RFP responses, including standard PPA’s, credit worthiness, ownership structure and other terms. | 6 | 2015-01-23 | 2015-01-23 | UIUC, PEI, FM | No change.
7 | Notification of award. | 1 | 2015-01-30 | 2015-01-30 | PEI | No change.
8 | Negotiate and execute PPA with winning bidder. | 13 | 2015-04-30 | 2015-04-30 | UIUC, PEI, FM | No change.
9 | Delivery begins. |  | 2015-07-01 | 2015-07-01 |  | No change.
| Total Time Estimate (weeks) | 40
UIUC = University of Illinois at Urbana-Champaign
PEI = Prairieland Energy, Inc.
FM = Fellon McCord