## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: |  | South Campus Pathway Lighting Improvements
Total Amount Requested from SSC: |  | 58886.61
Amount Requested as: |  | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task |  | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Dig and Pour Footings |  | 1 |  | 2018-03-23
Underground Electrical Work |  | 1 |  | 2018-03-30
Erect Poles |  | 1 |  | 2018-04-06
Fixture Electrical Work |  | 1 |  | 2018-04-13
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item |  | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Boring and 4" conduit (lf) |  | 1.23 | 900 | 1107
5kV XLP Cable (clf) |  | 163.3 | 9 | 1469.7
Control Cable (clf) |  | 35.28 | 9 | 317.52
10' x 3/4" Copper Plated Steel bar (ea) |  | 39.31 | 15 | 589.65
Poles (ea) |  | 1035.15 | 15 | 15527.25
Light Fixture (ea) |  | 1108.8 | 15 | 16632
Concrete (cy) |  | 330.03 | 8 | 2640.24
Electrical connection |  | 522.52 | 2 | 1045.04
Misc costs |  | 750 | 1 | 750
0
|  |  | Subtotal | 40078.4
Publicity & Communication
Digital signage |  |  |  | 100
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 100
Personnel & Wages
Boring and 4" conduit (lf) |  | 4.15 | 900 | 3735
5kV XLP Cable (clf) |  | 220.4 | 9 | 1983.6
Control Cable (clf) |  | 55.65 | 9 | 500.85
10' x 3/4" Copper Plated Steel bar (ea) |  | 113.51 | 15 | 1702.65
Poles (ea) |  | 429.78 | 15 | 6446.7
Light Fixture (ea) |  | 50.14 | 15 | 752.1
Concrete (cy) |  | 265.58 | 8 | 2124.64
Electrical connection |  | 732.83 | 2 | 1465.66
Misc costs |  |  |  | 0
0
|  |  | Subtotal | 18711.2
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal | 0
|  |  | TOTAL BUDGET | 58889.6
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
None
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
|  | Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
|  | Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
15 new lamps at 24.7 W/lamp on average 10 hrs/day (less set back to 50% approx 10% of time) = 2148 lb CO2/yr less replaced metal halide at 100 Watts = -610 lb CO2/yr for total increase of 1,538 lb CO2/yr for each vehicle not used, this will save 1 car driven 2 miles/day with average 23.6 mpg = 296 lb CO2/yr saved if just 5 cars are not driven, the CO2 contribution would be approximately equal. See below for detailed calculations
End of Application
| Energy/CO2 impact |  |  | cost
| 15 lamps @ 24.7 Watt each | 0.3705 | kWh
| operate average 10 hr/day | 1352.325 | kWh/yr
| 50% reduction (10% unoccupied) | -67.6162 | kWh/yr
| Total Energy Use | 1285.0793 | kWh/yr | 79.0348 | annual cost LED
| CO2 contribution @1.672 lb/kWh | 2148.6525 | lb CO2/year | 470.3025 | annual cost MH
| Less replaced Metal Halide |  |  | 391.2677 | savings
| 1 lamp @ 100 Watt | 365 | kWh | 150.5097
| CO2 contribution @ 1.672 lb/kWh | -610.28 | lb CO2/year
| Total Energy/CO2 impact | 1538.3725 | lb CO2/year | 5475 | if Metal Halide
|  |  |  | 9154.2 | lb CO2
Vehical Usage reduction
| 1 car drives 2 miles daily (180 days) | 360 | miles
| averaage mpg 23.6 | 15.2542 | gallons
| CO2 contribution @ 19.4 lb/gal | 295.9322 | lb CO2/year
| # cars to balance energy CO2 increase | 5.1984