## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Classroom LED Upgrades
Total Amount Requested from SSC: | 29500
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Design Phase: Field verification | 4 weeks |  | 2018-02-02
Design Phase: Product research | 3 weeks |  | 2018-02-23
Construction Phase: Ordering materials, scheduling work | 3 weeks |  | 2018-03-16
Construction Phase: Installing lamps | 14 weeks |  | 2018-06-29
Closeout Phase: Publicity work | 4 weeks |  | 2018-07-27
Closeout Phase: Energy analysis | 1 year |  | 2019-06-29
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
LED Lamps | 15 | 750 | 11250
A19 Extensions | 2.5 | 170 | 425
Dimmer Switches | 50 | 10 | 500
Spare lamps for "attic stock" | 15 | 75 | 1125
0
0
0
0
0
0
|  | Subtotal | 13300
Publicity & Communication
New signage at renovated rooms | 50 | 6 | 300
Signage design and approval | 300 | 1 | 300
0
0
0
0
0
0
0
0
|  | Subtotal | 600
Personnel & Wages
Field verification | 34.6 | 75 | 2595
Install LED Lamps | 34.6 | 300 | 10380
Install Dimmer Switches | 55 | 20 | 1100
Adjust dimming systems | 100 | 8 | 800
0
0
0
0
0
0
|  | Subtotal | 14875
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Contingency | 725 | 1 | 725
0
0
0
0
0
0
0
0
0
|  | Subtotal | 725
|  | TOTAL BUDGET | 29500
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
No other funding sources are included in this project.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
750 lamps multiplied by approx. 87 watts per lamp reduction (100W lamp to 13W lamp) = 65.25 kW reduction. Assuming 30 hours/week use per lamp, savings = 1957.5 kWh per week, or 101,790 kWh per year. This would equal 60,879 CO2lb reduction in greenhouse gases, and almost $8,000 in electricity savings per year.
End of Application