## Budget and Scope
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Geothermal exchange for greenhouses at UIUC Woody Perennial Polyculture Research Site
Total Amount Requested from SSC: | 132550
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Drill test hole, collect sediment core and geophysical log | 1 |  | 2018.07.09
Install geothermal loop and fiber-optic cable in borehole | 0.25 |  | 2018.07.13
Conduct thermal response test | 1 |  | 2018.07.20
Complete thermal property testing of core samples | 3 |  | 2018.07.25
Complete wellbore model and design geothermal borefield | 3 |  | 2018.08.03
Order and purchase field supplies and cables | 3 |  | 2018.08.03
Drill other boreholes, install geothermal loop with fiber-optic cables | 5 |  | 2018.09.14
Connect loops, install pumps, and extend piping to greenhouses | 3 |  | 2018.10.05
Install surface infrastructure (water lines, heat pumps, etc.) | 4 |  | 2018.11.21
Monitoring of geothermal system | 52 |  | 2019.11.21
Write/submit final report | 4 |  | 2019.12.20
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Drilling (20 boreholes) | 4000 | 20 | 80000
Downhole geophysical logging (1 borehole) | 1300 | 1 | 1300
Fiber optic cable and accessories | 2000 | 1 | 2000
Geothermal equipment (pumps, tubing, tanks, thermostats) | 43000 | 1 | 43000
0
0
0
0
0
0
|  | Subtotal | 126300
Publicity & Communication
Publicity & Communication fees | 250 | 1 | 250
0
0
0
0
0
0
0
0
0
|  | Subtotal | 250
Personnel & Wages
UIUC student science major (thermogeology characterization) | 15 | 120 | 1800
UIUC student engineering major (wellbore design) | 15 | 120 | 1800
UIUC student science major (geothermal system analysis) | 15 | 160 | 2400
0
0
0
0
0
0
0
|  | Subtotal | 6000
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 132550
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
The service time of the team members at the ISGS and Department of Civil and Environmental Engineering will be in-kind.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
Based on cursory calculations of propane usage and comparison to geothermal heating, a 20% reduction of CO2 emissions is expected. This estimate is also supported by findings by Niess (1998): https://intraweb.stockton.edu/eyos/energy_studies/content/docs/proceedings/NEISS.PDF
End of Application