## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Temple Hoyne Buell Hall as an Energy Learning Laboratory
Total Amount Requested from SSC: | 300000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Student project evaluating alternate window hardware | semester effort |  | Fall 2018
Window hardware: Finalize design and complete installation | semester effort |  | Spring 2019
DCV project: student evaluation of CO2 basline | semester effort |  | Spring 2019
Install Low-Leak Dampers and Implement DCV | 3 weeks |  | Summer 2019
DCV project: student evaluate performance and optimization | semester effort |  | Fall 2019
Lighting project: student project for design and input | semester effort |  | Fall 2018
Lighting project: finalize design and complete installation | 8-12 weeks |  | Spring 2019
Fault detection: Determine algorithms identifying BAS defficiencies | semester effort |  | Spring 2019 and Fall 2019
Dashboard project: student design | semester effort |  | Fall 2018 and Spring 2019
Finalize design and Implement Dashboard Solution | 8-12 weeks |  | Fall 2019
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Low-Leak Dampers & CO2 sensors with programming | 10000 | 4 | 40000
Window Hardware | 200 | 100 | 20000
Dashboard | 20000 | 1 | 20000
Lighting Upgrades | 200 | 650 | 130000
0
0
0
0
0
0
|  | Subtotal | 210000
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
SEDAC Student Labor - All Projects | 10 | 1000 | 10000
SEDAC Staff Labor - All Projects | 40 | 2000 | 80000
0
0
0
0
0
0
0
0
|  | Subtotal | 90000
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 300000
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
SEDAC has applied for funding through the University of Illinois Revolving Loan Fund for energy projects for TBH, but not directly related to the work to be performed under this proposal. The energy projects proposed under the Revolving Loan Fund are not directly related to the success of this application.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
The project will yield savings of 81,000 kWh; 320 klbs steam; $13,100 in energy costs, 214,000 lbs CO2 emissions towards the University of Illinois at Urbana-Champaign's energy reduction goals and iCAP goals.
End of Application