|  |  |
| --- | --- |
| Year Funding Allocated: | FY09 |
| Funding Amount: | $10,600.00 |
| Anticipated End Date: | November 30, 2009 |
| Project Leader Name: | Morgan Johnston |
| Project Leader Email/Phone: | [mbjohnst@illinois.edu](mailto:mbjohnst@illinois.edu)  217-333-2668 |
| Today’s Date: | Nov. 7, 2012 |

## Project Scope

Fill in an executive overview here. Include original project scope and describe progress toward the stated goal. Indicate changes to the scope of the project (previous or anticipated).

The goal of this project is to provide standard bicycle parking at three locations on campus: Freer Hall, the Undergraduate Library, and the Agricultural Engineering Sciences Building.  This will encourage bicycle riding and support the Campus Area Transportation Study (CATS) mission “to better accommodate pedestrian, bicycle, transit, and vehicle movements in a more user-friendly environment.”  This is also one of the amenities recommended by the University of Illinois at Urbana-Champaign Multi-Modal Transportation Study recommendation to “provide other amenities to accommodate existing bicyclists and attract new ones.”

The impacts are already visible: the racks at the Undergraduate Library are nearly always full, while the racks at Freer are used by not only students at Freer Hall, but students living at the Busey-Evans Residence hall as well. The Agricultural Engineering Sciences Building rack also remains full throughout the day.

## Timeline & Budget

Indicate project timeliness and budget as stated in application. Please indicate if the project is on schedule and within budget.

|  |  |  |  |
| --- | --- | --- | --- |
| Schedule item | Planned Date | Actual Date | Variations from Proposed Timeline |
| ARC approval | Jun 09 | Jun 09 | None |
| Racks ordered | Jul 09 | Oct 09 | delayed by Morgan’s learning curve |
| Racks installed | Fall 09 | Spring 10 | Delayed by weather |
|  |  |  |  |
| Budget item | **Expense Amount** | **Expense Date** | **Variations from Proposed Budget** |
| UGL racks | $5178.27 | Spring 2010 | None |
| Freer racks | $6726.41 | Spring 2010 | None |
| AESB racks | $1013.85 | Spring 2010 | None |
| Dept cost share | ($2,318.53) | Summer 2010 | None |

## Project Outreach

Please indicate how the project has been publicized (educational signage, newspaper, poster presentation, etc.). Please list publicity goals that have not yet been accomplished.

The project was publicized with stickers on the racks. The stickers say “Partially funded by the Student Sustainability Committee.” The existence of the racks did a lot for telling people about the project, since users immediately began using them. Additionally, there was a press release in 2009 about the project, which explained how the SSC funded the project.