## Final Project Report
SSC Budget and Timeline Form - Final Project Report
The SSC Budget and Timeline Form - Final Project Report must be completed upon completion of a project OR upon expiration of an award, whichever comes first. This form requires a complete list of updated project timelines and milestones for the project and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu
GENERAL PROJECT INFORMATION
| Project Title: | Geothermal Exchange at Greenhouses at UIUC Energy Farm
| Original Award Date (or Semester/Year)*: | 2018-04-15 | <*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): | 213550
| Total Expenses This Period**: | 390 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: |  | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Date of This Application Submission: | 2025-09-05
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the work you accomplished on the entire project. Include start and end dates and % complete). Be as detailed as possible so that the SSC can fully evaluate this project. Insert additional rows if necessary.
Task |  |  | Start Date | End Date (or estimated) | % Complete
Receive Underground Thermal Battery (UTB) from Oak Ridge National Laboratory (ORNL) |  |  | 2023-01-13 | 2023-01-13 | 100
Engineering design developed by WSP |  |  | 2022-11-15 | 2023-03-30 | 100
Construct 48-inch borehole for UTB installaton (Paid by PRI-IWRC grant) |  |  | 2023-02-28 | 2023-04-07 | 100
Construct four geothermal borefield that will be connecrted inline with the UTB |  |  | 2023-02-27 | 2023-03-13 | 100
Purchase 5-ton geothermal heat pump from Climate Master, Inc. |  |  | 2023-05-23 | 2023-05-23 | 100
F&S and project team meet to plan future work and seek additional funding |  |  | 2023-06-21 | 2025-07-19 | 100
F&S installs sensors for energy system at the Energy Farm (Paid by PRI-IWRC) |  |  | 2023-07-26 | 2023-08-23 | 100
SSC approves additonal funding |  |  | 2023-09-07 | 2023-09-07 | 100
F&S completes mechanical, electrical, and plumbing work in building |  |  | 2023-09-25 | 2024-01-26 | 100
Complete trenching to connect borefield to the building energy system |  |  | 2024-02-29 | 2024-03-12 | 100
F&S completes remaining work on the building energy system; geothermal system tested |  |  | 2024-03-13 | 2024-04-05 | 100
Geothermal system commissioned |  |  | 2024-05-02 | 2024-05-02 | 100
Geothermal system performance adjustment/maintanence and data collection |  |  | 2024-05-02 | 2025-09-05 | 100
EXPENSES
List all expenditures from this award made since the last semester report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  |  | Total Spent
Replace inverter drive on the geothermal heat pump (under warranty) |  |  |  | 390
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 390
Publicity & Communication
Item |  |  |  | Total Spent
Informational sign for project purchased and hung outside mechanical room |  |  |  | 35
Portable (outside) sign purchased to display information about the borefield |  |  |  | 0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  | 390