## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Orchard Downs Accessible Gardening
Total Amount Requested from SSC: | 17500 | Total Amount Allocated: | Leave blank if N/A
Date of Submission: | 11/16/23
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Constructing raised garden beds | 4 |  | 2024-03-01
Preparing the ground and adding the crushed granite | 2 |  | 2024-03-15
Creating accessible path to raised garden beds | 1 |  | 2024-03-15
Install water spigot | 1 |  | 2024-03-22
Install fence | 1 |  | 2024-03-29
Adding soil and bench | 1 |  | 2024-04-12
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
4'x 8'x 2' Raised Garden Bed, material wood (treated wood with labor is $345.36 but treated wood is not good for soil or plants, so a liner would be needed; if using cedar wood the cost is $961 which includes labor) $500 is noted in using treated wood and a liner; beds will be constructed by carpenters in University Housing. | 500 | 8 | 4000
30' x 50' decomposed crushed granite (area under the garden beds) includes material and labor | 7000 | 1 | 7000
Connecting water line and installing a water spigot (this includes labor and material) | 3000 | 1 | 3000
Black chain link fence (includes material and labor) | 3500 | 1 | 3500
0
0
0
0
0
0
|  | Subtotal | 17500
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 17500
End of Application