## Scope Change
SSC Budget and Timeline Form - Scope Change
The SSC Budget and Timeline Form - Scope Change must be completed and submitted with the SSC Scope Change Application. This form requires information about the originally awarded project as well as detailed information about the requested changes to the project's scope. Leave the Revised Scope & Schedule section or the Revised Budget section blank if not applicable to your Scope Change request If you have questions, please email SSC's general email, Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title as Indicated on Original Award: |  | Addressing Sustainability in Research: Pipette Tip Box Waste
| Original Award Date (or Semester/Year)*: |  | 2024-03-27 | <*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.
| Amount Originally Awarded by SSC: |  | 1818
| Remaining Unspent Funds in Original Award**: |  | 606 | <**NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Amount of Additional Funds Requested: |  | 96.63
| Expected Date of Project Completion: |  | 2025-05-01
| Date of This Scope Change Submission: |  | 2024-11-15
REVISED SCOPE & SCHEDULE
What is the revised plan for project implementation? Describe the key steps of the remaining project including the original estimated completion date for each item and the revised completion date as well as the required semester project reports and the required final project report. If there are new tasks not listed in the original award, indicate NEW for the original date. Be as detailed as possible so that the SSC can fully evaluate the merit of this Scope Change. Insert additional rows if necessary.
Task |  |  | Original Estimated Completion Date |  | REVISED Estimated Completion Date
Finish Handing Out Pipette Tip Recycling Boxes |  |  | 2024-10-15 |  | 2025-02-01
Purchase and Receive Alcohol Wipe Recycling Boxes |  |  | NEW |  | 2025-02-01
End Date (Submit Final Report and Collect Feedback from Labs) |  |  | 2024-12-01 |  | 2025-05-01
REVISED BUDGET
List all budget items for which funding is being requested under the appropriate category. Indicate whether it is a new item in the original budget or a revised item. Be as detailed as possible so that the SSC can fully evaluate the merit of this Scope Change. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
Small Zero Waste Box™ for synthetic disinfectant wipes (iBuy) |  | New | 96.63 | 1 | 96.63
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  |  | 96.63
Equipment & Construction Costs (If Additional Budget Request Denied)
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
Small Zero Waste Box™ for synthetic disinfectant wipes (iBuy) |  | New | 96.63 | 2 | 193.26
Fisherbrand™ Pipette Tip Recycle Box, Pack of 5 (~1/2 the size of the TerraCycle pipette tip box bins) |  | Revised | 341.5 | 1 | 341.5
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  |  | 534.76
Note: In the assumption that the the additional budget request is denied (above), I will purchase 2 packs of the alcohol wipes and will have $71.24 of my award left, which will be rescinded due to not having enough funding to purchase another pack of the Fisherbrand ($341.50) or TerraCycle recycling boxes ($606).