## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | G6 Max
Total Amount Requested from SSC: | 10000 | Total Amount Allocated: | Leave blank if N/A
Date of Submission:
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Complete Improved Body Panels - Remanufacture composite body panel using G6 molds. These molds have improved load bearing features to avoid shortcoming of G6. | 8 weeks |  | 2023-11-05
Manufacture New Power Train Components - There were several components we can not manufacture on campus. We plan on outsourcing these integral components which will help increase efficiency of the vehicle tremendously. | 6 weeks |  | 2023-10-15
Complete Mechanical system Improvements- there are several systems that can be remanufactured, tested, and optomized to decrease fiction and drag and increase energy efficiency. | 8 weeks |  | 2023-11-05
First Drive Day - Drive day will serve to be the first test for all the short term projects | 9 weeks |  | 2023-11-12
Finish Design and Order Electrical Components - All the electrical componenets are integral for the car. | 11 weeks |  | 2023-11-26
Test and Redesign - testing all of the components of the car in order to ensure all systems work well together and catch any shortcomings | 23 weeks |  | 2024-02-11
Second Drive Day - conduct a mock technical inspection on final designs and test all components interaction while driving | 24 weeks |  | 2024-02-18
Competition - represent UIUC at a international compeition to determine the effiecincy of the vehicle. | 32 weeks |  | 2024-04-14
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Aluminium 7075 Stock | 250 | 2 | 500
Carbon Steel Stock | 300 | 3 | 900
Tires | 50 | 3 | 150
Wheel Rims | 100 | 3 | 300
Brakes | 100 | 3 | 300
Miscellaneous Hardware | 50 | 1 | 50
3D printing costs | 350 | 1 | 350
Wheel Hub Bearings | 75 | 6 | 450
Honda GHX50 Parts | 500 | 1 | 500
Custom Parts Manufacturing Costs | 3000 | 1 | 3000
PCBs | 900 | 1 | 900
PCB components | 500 | 1 | 500
Brushless Motor | 400 | 1 | 400
STM 32 Boards | 100 | 4 | 400
Sensors | 30 | 5 | 150
Wiring Harness | 200 | 1 | 200
Bondo | 100 | 1 | 100
Polycarbonate Sheets | 100 | 2 | 200
Carbon Fiber Sheets | 200 | 2 | 400
Liquid Resin | 125 | 2 | 250
|  | Subtotal | 10000
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 10000
End of Application