## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Illini Lights Out
Total Amount Requested from SSC: | 4000 | Total Amount Allocated:
Date of Submission: | 9/13/2023
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Illini Lights Out first planning meeting | N/A |  | Mid January
ILO Events 1-5 (Spring) | 2nd semester |  | January-May
Semesterly Project Report | 1 week |  | May
Intern Transition Meeting | N/A |  | May
iSEE Staff Initial Semester Meeting | N/A |  | Mid August
ILO Events 6-10 (Fall) | 1st semester |  | September-December
Semesterly Project Report | 1 week |  | December/January
ILO Events 11-15 (Spring) | 2nd semester |  | January-May
Semesterly Project Report | 1 week |  | May
Intern Transition Meeting | N/A |  | May
iSEE Staff Initial Semester Meeting | N/A |  | August
ILO events 16-20 (Fall) | 1st semester |  | September-December
Semesterly Project Report | 1 week |  | December/January
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
insentives | 200 | 20 | 4000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 4000
|  | TOTAL BUDGET | 4000
End of Application