## Scope Change
SSC Budget and Timeline Form - Scope Change
The SSC Budget and Timeline Form - Scope Change must be completed and submitted with the SSC Scope Change Application. This form requires information about the originally awarded project as well as detailed information about the requested changes to the project's scope. Leave the Revised Scope & Schedule section or the Revised Budget section blank if not applicable to your Scope Change request If you have questions, please email SSC's general email, Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title as Indicated on Original Award: |  | Intersectional Environmental Justice Series
| Original Award Date (or Semester/Year)*: |  | Fall 2024 | <*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.
| Amount Originally Awarded by SSC: |  | 29480
| Remaining Unspent Funds in Original Award**: |  | 22472.1 | <**NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Amount of Additional Funds Requested: |  | 0
| Expected Date of Project Completion: |  | 2026-05-25
| Date of This Scope Change Submission: |  | 2024-09-19
REVISED SCOPE & SCHEDULE
What is the revised plan for project implementation? Describe the key steps of the remaining project including the original estimated completion date for each item and the revised completion date as well as the required semester project reports and the required final project report. If there are new tasks not listed in the original award, indicate NEW for the original date. Be as detailed as possible so that the SSC can fully evaluate the merit of this Scope Change. Insert additional rows if necessary.
Task |  |  | Original Estimated Completion Date |  | REVISED Estimated Completion Date
recruit and review applications for a Summer/Fall 2023 Ecofeminism Summit intern |  |  | 2024-06-01 |  | completed
Review feedback from the Spring 2022 and Spring 2023 Ecofeminism Summits |  |  | 2024-06-14 |  | completed
Identify potential campus partners and form a fall 2023 planning committee |  |  | 2024-06-14 |  | completed
Host bi-weekly planning committee meetings to determine learning objectives, identify speakers and activities, and develop assessment tool |  |  | 2024-07-31 |  | 2024-11-15
Invite identified speakers and confirm dates |  |  | 2024-08-14 |  | 2024-10-31
Finalize Schedule and develop marketing |  |  | 2024-08-14 |  | 2024-10-31
Promote week of events on digital signage |  |  | 2024-12-01 |  | 2024-12-01
Host events |  |  | 2024-12-01 |  | 2024-12-01
Evaluate outcomes |  |  | 2024-10-31 |  | 2024-12-18
Submit final report |  |  | 2025-02-15 |  | 2025-02-15
REVISED BUDGET
List all budget items for which funding is being requested under the appropriate category. Indicate whether it is a new item in the original budget or a revised item. Be as detailed as possible so that the SSC can fully evaluate the merit of this Scope Change. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  |  | 0
Publicity & Communication
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
Digital Signage (Housing, $40/week) |  | No | 40 | 1 | 40
Digital Bulletin Boards (Illini Union, $75/week) |  | No | 75 | 2 | 150
Digital Bulletin Boards (Campus Rec, $75/week) |  | No | 75 | 2 | 150
Printing for program materials |  | No | 250 | 1 | 250
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  |  | 590
Personnel & Wages
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
Summer Ecofeminism Summit Intern Wages ($14/hr, 10 hrs/wk for 8 weeks) |  | No | 14 | 80 | 1120
Fall Ecofeminism Summit Intern Wages ($14/hr, 10 hrs/wk for 16 weeks) |  | No | 14 | 160 | 2240
Fringe Benefits for Intern (Social Security, Medicare, Work Comp) |  | No | 1 | 75 | 75
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  |  | 3435
General Supplies & Other
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
Honorarium |  | Revised | 1500 | 2 | 3000
| Honorarium (remaining unallocated) | Revised | 9000 | 1 | 9000
Film Screening Rights |  | Revised | 350 | 1 | 350
Books for Book Clubs (NAH - Braiding Sweetgrass) |  | Revised | 11.33 | 50 | 566.5
Books for Book Clubs (WRC - Parable of the Sower) |  | Revised | 19.99 | 25 | 499.75
Prizes for Trivia |  | Revised | 15 | 0 | 0
Giveaways (Water bottles) |  | Revised | 12.15 | 117 | 1421.55
| Giveaways (Bento Boxes) | Revised | 9.58 | 150 | 1437
| Giveaways (T-Shirts) | Revised | 20 | 25 | 500
Stickers |  | No | 0.4 | 2250 | 900
Room Rental |  | No | 400 | 5 | 2000
Food expense for sustainable middle eastern cooking demo and marketplace event |  | No | 1000 | 1 | 1000
Sustainable Servingware (plates, forks, cups, etc) |  | No | 4000 | 1 | 4000
Bus Rental for IE farm field trip |  | Revised | 650 | 1 | 650
General Supplies & Other Subtotal |  |  |  |  | 25324.8
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  |  | 0
|  |  |  | TOTAL REVISED BUDGET | 29349.8