## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Temple Hoyne Buell Hall DDC Upgrade of Room Equipment
Total Amount Requested from SSC: | 150000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Network and power conduit run installation | 8 weeks |  | 2023-08-18
Occupancy sensor conduit & infrastructure installation | 12 weeks |  | 2023-10-13
Piping modifications and valve replacements | 4 weeks |  | 2023-10-13
Controller and thermostat installation | 8 weeks |  | 2023-11-24
Controller switchover and programming | 3 weeks |  | 2023-12-15
Existing equipment demolition | 3 weeks |  | 2024-01-19
Test, adjusting and balancing | 4 weeks |  | 2024-01-19
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Controller enclosure | 40 | 98 | 3920
Siemens DXR Controller | 322.17 | 98 | 31572.66
Temperature sensor | 25 | 98 | 2450
Siemens Thermostat | 119.92 | 98 | 11752.16
Valve actuator | 400 | 194 | 77600
Valves | 300 | 35 | 10500
Misc electrical | 19000 | 1 | 19000
Misc piping | 3000 | 1 | 3000
Occupancy sensors | 250 | 150 | 37500
0
|  | Subtotal | 197294.82
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Contract Electrician | 97.05 | 2360 | 229038
Temperature Control Mechanic (Shop PM) | 68.59 | 750 | 51442.5
Electrician (Shop PM) | 68.59 | 750 | 51442.5
Sheet Metal Worker (Shop PM) | 68.59 | 400 | 27436
Programmer (Shop SJ) | 91.34 | 160 | 14614.4
Pipefitter (Shop 23) | 80 | 320 | 25600
0
0
0
0
|  | Subtotal | 399573.4
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 596868.22
End of Application