## Final Project Report
SSC Budget and Timeline Form - Final Project Report
The SSC Budget and Timeline Form - Final Project Report must be completed upon completion of a project OR upon expiration of an award, whichever comes first. This form requires a complete list of updated project timelines and milestones for the project and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Part 2 Temple Hoyne Buell Hall DDC Upgrade of Room Equipment
| Original Award Date (or Semester/Year)*: | 2023-12-04 | <*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): | 33655.03
| Total Expenses This Period**: | 33655.03 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: | 0 | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Date of This Application Submission: | 2025-02-03
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the work you accomplished on the entire project. Include start and end dates and % complete). Be as detailed as possible so that the SSC can fully evaluate this project. Insert additional rows if necessary.
Task |  |  | Start Date | End Date (or estimated) | % Complete
Network and power conduit run installation |  |  |  | 2023-08-18 | 100%
Occupancy sensor conduit & infrastructure installation |  |  |  | 2023-10-13 | 100%
Piping modifications and valve replacements |  |  |  | 2023-10-13 | 100%
Controller and thermostat installation |  |  |  | 2023-11-24 | 100%
Controller switchover and programming |  |  |  | 2023-12-15 | 100%
Existing equipment demolition |  |  |  | 2024-01-19 | 100%
Test, adjusting and balancing |  |  |  | 2024-01-19 | 100%
EXPENSES
List all expenditures from this award made since the last semester report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 0
Publicity & Communication
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  |  |  | Total Spent
Contract Electrician |  |  |  | 33655.03
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 33655.03
General Supplies & Other
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  | 33655.03