## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Steven S. Wymer Hall (Wymer Hall) Formerly the South Campus Center for Interdisciplinary Learning (SCCIL), renamed Steven S. Wymer Hall at the Board of Trustees meeting on March 30, 2023.
Total Amount Requested from SSC: | 500000 | Total Amount Allocated: | 200000
Date of Submission: | 4/30/24
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Ceremonial Groundbreaking |  |  | 2023-04-14
Construction Start | 87 weeks 2 days (to Substantial Completion) Construction is currently on schedule! |  | 2023-05-08
Geothermal Field - Contractor Mobilization |  |  | December 4-15, 2023
Geothermal Field - Day 1 - Begin drilling operations |  |  | 2023-12-20
Geothermal Field - Drill rigs demobilized - Drilling of 70 450' deep geothermal wells complete |  |  | Week of February 19-23, 2024
Geothermal Field - Continue geothermal well field underground connections to Wymer Hall |  |  | February 23, 2024 - April/May, TBD. Anticipate Spring completion. Weather dependent. Rough grading underway in order to seed military axis (geo field) in Spring.
Substantial Completion (SC) |  |  | 2025-01-07
Commissioning / Owner Move-In / Soft Opening |  |  | Spring / Summer 2025
Final Report to SSC |  |  | Spring 2025
First Classes Held |  |  | Fall 2025
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Contractor - Item | Contractor's Schedule of Values | Billed to Date
Equipment & Construction Costs
SB - Equipment | 2212412 | 1477570.3
*A&R - Geothermal Equipment and Install | 4331358.24 | 1787122.45
TOTAL - Geothermal Equipment and Install | 6543770.24 | 3264692.75
*A&R - Geothermal Field Only (included in above) | 970000 | 704750 | 500000
Geothermal Field - Spring 2023 SSC Award | -100000 |  | -100000
Geothermal Field - Fall 2023 SSC Award | -100000 |  | -100000
Landscaping and Repair at Military Axis (estimated cost) | 55300 |  | 0
|  | Subtotal | 300000
Publicity & Communication
Digital Screens and SSC Cross-Promotion Opportunities (to be coordinated with Gies Marketing & Communications) | To Be Determined |  | 0
SSC physical signage acknowledgement | To Be Determined |  | 0
Geothermal webstory on Gies Business webpage | https://giesbusiness.illinois.edu/news/2024/01/03/wymer-hall-going-geothermal-to-enhance-sustainability |  | 0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 300000
End of Application