## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Power Station
Total Amount Requested from SSC: | 3950 | Total Amount Allocated: | 3950
Date of Submission: | 12/14/2024
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
(Completed) Design theory and parts research | 12 |  | 2024-04-15
(Completed) Initial 18650 battery test assembly | 2 |  | 2024-03-19
(Completed) Prototype system parts research and design | 2 |  | 2024-03-13
(Completed) Prototype assembly | 1 |  | 2024-03-20
(Completed) Prototype testing | 1 |  | 2024-03-23
(Completed) 18650 battery assembly [Batch-2] | 2 |  | 2024-04-06
(Completed) Order and receive Power Station parts | 2 |  | 2024-05-01
(Completed) Power Station initial test integration | 1 |  | 2024-05-10
(Completed) Stress test current design | 1 |  | 2024-06-04
(Completed) Research requirements of new design | 10 |  | 2024-12-01
Assemble remaining 18650 batteries | 2 |  | 2025-02-01
Write documentation for 18650 assembly | 1 |  | 2025-02-08
Design better internal mounting for Power Station | 6 |  | 2025-03-01
Complete assembly of new design | 6 |  | 2025-04-15
Complete final report and other documentation (throughout) | 2 |  | 2025-05-05
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs (Current Purchases)
Battery Tester | 36.98 | 1 | 36.98
Battery Fish Paper | 20.59 | 1 | 20.59
18650 Protection Circuits | 9.99 | 6 | 59.94
18650 Heathshrink Spool | 6.2 | 1 | 6.2
12V LifePO4 Battery | 970.01 | 1 | 970.01
Battery Charging Equipment | 138.41 | 1 | 138.41
Fuse Block and Battery Switch | 115.71 | 1 | 115.71
Automotive Fuses | 81.82 | 1 | 81.82
2000W Pure Sine Wave Inverter | 275.49 | 1 | 275.49
400W Portable Solar Panels | 626.99 | 1 | 626.99
Solar MPPT Charge Controller | 382.5 | 1 | 382.5
Solar Panel Cabling and Display | 87.98 | 1 | 87.98
USB-C Power Delivery Charger/Port | 53.05 | 1 | 53.05
DC Regulators (9V, 12V, 5V, 3.3V) | 90.07 | 1 | 90.07
Storage Crate | 97.48 | 1 | 97.48
Prototype Wire and Harnessing Supplies | 236.27 | 1 | 236.27
Wire and Harnessing Supplies | 256.8 | 1 | 256.8
Crimping Tools | 51.26 | 1 | 51.26
Raw Material (Wood/Acrylic) | 151.27 | 1 | 151.27
3D Printer Enclosure and Filament | 233.61 | 1 | 233.61
0
|  | Subtotal | 3972.43
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 3972.43
End of Application