## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Power Station
Total Amount Requested from SSC: | 3950 | Total Amount Allocated:
Date of Submission: | 10/18/2023
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Finalize System Architecture (Parts Research) | 3 |  | 2023-11-20
Preliminary Parts Order | 1.5 |  | 2023-11-30
Preliminary Protoype (Extended due to break) | 3 |  | 2024-02-01
System Testing | 1.5 |  | 2024-02-13
Modifications / Bug Fixes | 4 |  | 2024-03-13
Field Test | 1 |  | 2024-03-20
Final Modifications & Parts Ordering | 5 |  | 2024-04-24
Fall Semester 2023 Report | 1 |  | 2023-12-03
Spring Semester 2024 Report | 1 |  | 2024-05-01
Docuementation + Open Source Blog Posts | 3 |  | 2024-05-07
Final Report | 2 |  | 2024-05-07
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Solar Panels w/ Charge Controller | 500 | 1 | 500
12V LifePo4 Batteries | 400 | 2 | 800
Pure Sinewave Inverter | 400 | 1 | 400
12V High Current Battery Charger | 300 | 1 | 300
Battery Management System | 150 | 1 | 150
Waterproof 100W USB-C Charging Panel | 50 | 1 | 50
Waterproof Status Monitoring Panel | 50 | 1 | 50
Waterproof Project Case | 350 | 1 | 350
Recessed Waterproof 12V DC Panel Connectors | 25 | 1 | 25
Recessed Waterproof AC Panel Connectors | 50 | 1 | 50
External Waterproof Cable Connectors | 50 | 1 | 50
Internal Cable Connectors | 30 | 1 | 30
Resettable Fuses | 75 | 1 | 75
Wire Lugs | 25 | 1 | 25
Wire Lugs Crimping Tool | 35 | 1 | 35
2 AWG Wire 10ft Red | 35 | 1 | 35
2 AWG Wire 10ft Black | 35 | 1 | 35
Heatshrink Kit | 25 | 1 | 25
Split Sleeve Wire Loom Cable Harnessing | 30 | 1 | 30
Extension Cord 50 ft | 40 | 1 | 40
Power Brick | 25 | 1 | 25
16 AWG Wire Red & Black | 50 | 1 | 50
18650 Battery Nickel Strips | 20 | 1 | 20
18650 Battery Heat Wrap | 20 | 1 | 20
18650 Battery Wire Leads + Connectors | 50 | 1 | 50
18650 Battery Protection Circuitry | 200 | 1 | 200
0
|  | Subtotal | 3420
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
Parts Shipping + Tax | 330 | 1 | 330
Design Reworks, Unaccounted Costs, Safety Buffer | 200 | 1 | 200
|  | Subtotal | 530
|  | TOTAL BUDGET | 3950
End of Application