## Semester Project Report
SSC Budget and Timeline Form - Semester Project Report
The SSC Budget and Timeline Form - Semester Project Report must be completed and submitted every semester regarless of the original application type. This form requires a list of updated project timelines and milestones and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Precious Plastics UIUC Recycling Station
| Original Award Date (or Semester/Year)*: | 2024-05-25 | (<*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.)
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): | 48961.99
| Total Expenses This Period**: | 29194.12 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: | 19767.87 | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Expected Date of Project Completion: | 2026-08-01
Date of This Application Submission:
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the progress you have made on the project since your last semester report. Include start and end dates and % complete). Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the progress of this project. Insert additional rows if necessary.
Task |  |  | Start Date | End Date (or estimated) | % Complete
Develop space for the Precious Plastics UIUC equipment at SCD, using the existing loading garage and storage cages |  |  | 2024-06-05 | 2024-08-09 | 100
Order equipment from FilaBot and Precious Plastics, ~8 weeks for delivery |  |  | 2024-07-01 | 2024-10-15 | 100
Assemble equipment in place |  |  | 2024-10-15 | 2024-12-05 | 100
Perform test runs using waste from SCD plastics |  |  | 2024-11-01 | 2024-12-05 | 100
Develop and implement training standards for equipment use by staff and students |  |  | 2024-11-01 | 2024-12-05 | 50
Debut and promote recycling station at Maker Network 25, an event produced at SCD that brings campus makers and facility managers together |  |  | 2025-01-07 | 2025-01-15 | 100
Develop collection process and sites across campus in collaboration with the Maker Network RSO and facility managers |  |  | 2025-01-20 | 2025-03-14 | 20
Develop a distribution or sales process for returning recycled acrylic sheets and 3D printing filament to facilities that provided them for use by students |  |  | 2025-03-24 | 2025-05-02 | 0
Establish metrics and reporting needs for waste diversion and promotion of the program on and off campus; use data and stories to seek additional contributors, collaborators, or funds to expand the program |  |  | 2025-06-01 | 2025-07-31 | 10
Submit a final report on the project that includes details on the recycling center, operations and policies, and metrics on initial use and waste diversion |  |  | 2025-07-15 | 2025-07-31 | 0
EXPENSES
List all expenditures from this award made since the last submitted semester project report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  |  | Total Spent
FilaBot Full Recycling Setup (https://www.filabot.com/products/full-recycling-setup?variant=32985846349899) |  |  |  | 26396.05
Materials and Supplies |  |  |  | 306.89
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 26702.94
Publicity & Communication
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  |  |  | Total Spent
Student Wages- Spring 2025 |  |  |  | 1585.74
Student Wages- Fall 2025 |  |  |  | 443.56
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 2029.3
General Supplies & Other
Item |  |  |  | Total Spent
Materials and Supplies, Spring 2025 |  |  |  | 306.89
Supplies, Fall 2025 |  |  |  | 154.99
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 461.88
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  | 29194.12