## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Precious Plastics UIUC Recycling Station
Total Amount Requested from SSC: | 48961.99 | Total Amount Allocated: | Leave blank if N/A
Date of Submission: | 4/25/2024
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Develop space for the Precious Plastics UIUC equipment at SCD, using the existing loading garage and storage cages | 6/5/24 - 8/9/2024 (4 weeks, Summer Intern project) |  | 2024-08-09
Order equipment from FilaBot and Precious Plastics | 6/14/24 - 7/1/24 (2 weeks to order) 7/1/24 - 10/15/24 (8 weeks for delivery) |  | Order completed by 7/1/2024 Equipment received by 10/15/2024
Assemble equipment in place | 10/15/24-12/5/24 (6 weeks) |  | 2024-12-05
Perform test runs using waste from SCD plastics | 11/1/24 - 12/5/24 (4 weeks) |  | 2024-12-05
Develop and implement training standards for equipment use by staff and students | 11/1/24 - 12/5/24 (4 weeks) |  | 2024-12-05
Debut and promote recycling station at Maker Network 25, an event produced at SCD that brings campus makers and facility managers together | 1/7/25 - 1/15/2025 (1 week) |  | 2025-01-15
Develop collection process and sites across campus in collaboration with the Maker Network RSO and facility managers | 1/20/25 - 3/14/25 (8 weeks) |  | 2025-03-14
Develop a distribution or sales process for returning recycled acrylic sheets and 3D printing filament to facilities that provided them for use by students | 3/24/25 - 5/2/25 (8 weeks) |  | 2025-05-02
Establish metrics and reporting needs for waste diversion and promotion of the program on and off campus; use data and stories to seek additional contributors, collaborators, or funds to expand the program | 6/1/25 - 7/31/25 (8 weeks, Summer Intern project) |  | 2025-07-31
Submit a final report on the project that includes details on the recycling center, operations and policies, and metrics on initial use and waste diversion | 7/15/25 - 7/31/25 (2 weeks, Summer Intern project) |  | 2025-08-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
FilaBot Full Recycling Setup (https://www.filabot.com/products/full-recycling-setup?variant=32985846349899) | 21646.99 | 1 | 34461.99
Storage Bins for raw waste and sorting: Industrial rolling waste bins | 150 | 10 | 1500
0
0
0
0
0
0
0
|  | Subtotal | 35961.99
Publicity & Communication
Information posters, decals, and materials for training and administration of the program |  |  | 1000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 1000
Personnel & Wages
Receive and assemble equipment (student labor hours) | 15 | 320 | 4800
Test run equipment and develop operating processes (student labor hours) | 15 | 480 | 7200
0
0
0
0
0
0
0
0
|  | Subtotal | 12000
Project Budget per F&S
0
0
0
0
0
0
0
0
0
|  |  | 0 | 48961.99
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 48961.99
End of Application