## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Red Oak Rain Garden Outreach and Enhancements
Total Amount Requested from SSC: | 9708.2 | Total Amount Allocated: | Leave blank if N/A
Date of Submission:
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
SIGNAGE
Continue the development of content and graphic design with RORG Team, Student Team, DRES, and F&S | 18 |  | 2024-08-16
Work with F&S and Sign Shop on design and location of signage | 18 |  | 2024-08-16
Final draft of the graphic design of the signage. | 18 |  | 2024-08-16
F&S Sign Shop print signage | 19 |  | 2024-08-16
F&S Sign Shop installs signage | 27 |  | 2024-10-18
PLANTS
Finalize plant order with Midwest Groundcovers | 4 |  | 2024-05-10
Arrange storage space at greenhouses for mid-September | 8 |  | 2024-06-07
Arrange RSO involvement in plant installation | 19 |  | 2024-08-26
Plants delivery | 22 |  | 2024-09-16
RORG Team, Student Team, CCMG, ECIMN, RSOs install plants | 22 |  | 2024-09-20
Final Report to SSC | 35 |  | 2024-12-13
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Large Sign | 300 | 3 | 900
Large Sign Brackets | 300 | 3 | 900
Large Sign Installation | 500 | 3 | 1500
Medium Sign | 150 | 3 | 450
Medium Sign Brackets | 250 | 3 | 750
Medium Sign Installation | 500 | 3 | 1500
Small Sign | 75 | 1 | 75
Small Sign Installation | 300 | 1 | 300
0
0
0
0
|  | Subtotal | 6375
Publicity & Communication
Done in-house and through Illinois Extension |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
REPLACEMENT & ENHANCEMENT PLANTS
Asarum canadense | 4.3 | 110 | 473
Carex pensylvanica | 1.5 | 360 | 540
Dryopteris marginalis | 10.5 | 50 | 525
Liatris aspera | 4.05 | 20 | 81
Lobelia cardinalis | 1.39 | 114 | 158.46
Phlox divaricata | 1.39 | 114 | 158.46
Rudbeckia fulgida | 1.39 | 76 | 105.64
Ruellia humilis | 1.39 | 76 | 105.64
Schizachyrium 'Prairie Blues' | 9.25 | 30 | 277.5
Sporobolus heterolepis | 7.15 | 30 | 214.5
DELIVERY |  |  | 344
Soil Amendments |  |  | 350
|  | Subtotal | 3333.2
|  | TOTAL BUDGET | 9708.2
End of Application