## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | SegBin.ai by TerraVortex
Total Amount Requested from SSC: | 3186.14 | Total Amount Allocated: | Leave blank if N/A
Date of Submission: | 02/09/2024
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Get the CAD ready | 4 weeks |  | 7th March 2024
Improve machine learning model | 4 weeks |  | 7th March 2024
3D Printing and manufacturing | 3 weeks |  | 28th March 2024
Testing the bin and adding finishing touches | 1 week |  | 4th April
Deploy both bins at the given locations |  |  | 5th April
Make improvements based on feedback | 2 weeks |  | 19th April
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
8020 25 Seires Aluminum Rails | 407.496 | 2 | 814.992
8020 Standard Size T-Nut | 1.8 | 22 | 39.6
m6x10 hex screws | 11.1 | 2 | 22.2
25 seriers 5 hole plate | 11.3 | 36 | 406.8
m6x10 screws and nut | 3.6 | 36 | 129.6
Walut Ply MDF core lasercut wood | 53.98 | 1 | 53.98
Raspberry Pi 5 8GB with case | 120 | 4 | 480
13.3 Inch Display | 75 | 2 | 150
IR sensors | 15.99 | 3 | 47.97
AWS EC2 Instance | 75 | 1 | 75
|  | Subtotal | 2220.142
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Wires and Connectors | 200 | 2 | 400
Machining Tools | 30 | 2 | 60
GPIO Extender | 30 | 2 | 60
Camera | 30 | 6 | 180
Motors | 29 | 4 | 116
Miscallaneous Expenses | 50 | 1 | 50
Shipping costs | 100 | 1 | 100
|  |  | 0 | Mi
0
0
|  | Subtotal | 966
|  | TOTAL BUDGET | 3186.142
End of Application