## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Towards Zero Waste: Classification via Spectroscopy Enabled Computer Vision at Campus Waste Transfer Station
Total Amount Requested from SSC: | 161200 | Total Amount Allocated: | Leave blank if N/A
Date of Submission: | Nov 16, 2023
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Develop a Lab-Scale waste classification system | 8 |  | 2024-02-01
Build a Spectral Library | 8 |  | 2024-03-01
Image-Based Classification of Waste Streams | 8 |  | 2024-06-01
Fuse image-based classification with spectroscopy data to develop an integrated MSW classification system | 8 |  | 2024-08-01
Miniaturized to a full-fledged waste classification system | 8 |  | 2024-10-01
Classify waste at the Materials Recovery Facility via the integrated waste classification system | 8 |  | 2024-12-01
Refine the Image-Based classification to augment classification accuracy | 8 |  | 2025-02-01
Modify the integrated waste classification system to improve classification accuracy | 8 |  | 2025-03-01
Techno-economic Analysis | 8 |  | 2025-06-01
Lifecycle Analysis (LCA) | 8 |  | 2025-08-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Materials Testing per hour | 50 | 100 | 5000
Near Infrared Spectrometer (NIR) | 25000 | 1 | 25000
0
0
0
0
0
0
0
0
|  | Subtotal | 30000
Publicity & Communication
Publications in scientific peer reviewed journals | 2500 | 2 | 5000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 5000
Personnel & Wages
2 Graduate students for 2 years (@50% RA in Fall and Spring) | 50000 | 2 | 100000
4 Undergraduate student for 2 years (@$15/hr x 4 hrs/week x 40 weeks/year for each student) | 4800 | 4 | 19200
0
0
0
0
0
0
0
0
|  | Subtotal | 119200
Project Budget per F&S
Hourly Staff at Waste Transfer Station (for equipment installation on the conveyor belt, as needed) | 50 | 100 | 5000
Wi-Fi and Power Supply | 2000 | 1 | 2000
0
0
0
0
0
0
0
0
|  | Subtotal | 7000
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 161200
End of Application