## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | SPARK
Total Amount Requested from SSC: | 1980 | Total Amount Allocated:
Date of Submission: | 10/18/2023
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
MK1 Schematic Design | 5 |  | 2023-10-26
MK1 Layout Design | 2.5 |  | 2023-11-09
MK1 Assembly | 1 |  | 2023-11-16
MK1 Testing | 3 |  | 2023-12-07
MK2 Design Revisions | 4 |  | 2024-01-15
MK2 Assembly | 2 |  | 2024-02-05
MK2 Testing | 3 |  | 2024-02-12
Final Modifications & Parts Ordering | 6 |  | 2024-04-24
Fall Semester 2023 Report | 1 |  | 2023-12-03
Spring Semester 2024 Report | 1 |  | 2024-05-01
Documentation + Open Source Blog Posts | 3 |  | 2024-05-07
Final Report | 3 |  | 2024-05-07
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Saleae Logic Analyzer | 1000 | 1 | 1000
PCB Manufacturing Costs | 100 | 2 | 200
SPARK Surface Mount Passive Components | 60 | 1 | 60
SPARK Surface Mount IC Components | 400 | 1 | 400
Soldering Paste + Other Consumables | 45 | 1 | 45
Wires & Connectors | 55 | 1 | 55
0
0
0
0
|  | Subtotal | 1760
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
Parts Shipping + Tax | 100 | 1 | 100
Design Revisions, Unnacounted for costs | 120 | 1 | 120
|  | Subtotal | 220
|  | TOTAL BUDGET | 1980
End of Application