## Sheet1
SSC Supplemental Budget and Timeline Form
Please use the SSC Supplemental Budget and Timeline Form for submission with the SSC Funding Application Step 2, SSC Funding Application Student Led Under $10,00.00, or the Semester/Final reports. All applications require an extensive list of expenditures for the use of budget variation for the SSC and its stakeholders. Additionally, this form requires a list of all project timelines and milestones. If you have any questions about the material present, please reach out to the SSCs general email, Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | SPARK
Total Amount Requested from SSC: | 1980 | Total Amount Allocated: | 1980
Date of Submission: | 5/10/2024
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
(Completed) MK1 Schematic Design | 12 |  | 2024-04-09
(Completed) MK1 Layout Design | 3 |  | 2024-04-30
Review MK1 Design | 6 |  | 2024-08-01
MK1 Assembly | 1 |  | 2024-09-01
MK1 Testing | 3 |  | 2024-09-22
MK2 Design Revisions | 6 |  | 2025-01-01
MK2 Assembly | 2 |  | 2025-01-20
MK2 Testing | 3 |  | 2025-02-10
Documentation + Open Source Blog Posts | 3 |  | 2025-04-10
Final Report | 3 |  | 2025-05-05
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs (Current Purchases)
Logic Analyzer | 264 | 1 | 264
Torque Driver | 127.14 | 1 | 127.14
Wire Ferrules and Crimping Tool | 48.96 | 1 | 48.96
Wire Harnessing Supplies | 90.42 | 1 | 90.42
USB Power Analyzer & Crimping Tool | 69.49 | 1 | 69.49
0
0
0
0
0
|  | Subtotal | 600.01
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 600.01
End of Application