## Scope Change
SSC Budget and Timeline Form - Scope Change
The SSC Budget and Timeline Form - Scope Change must be completed and submitted with the SSC Scope Change Application. This form requires information about the originally awarded project as well as detailed information about the requested changes to the project's scope. Leave the Revised Scope & Schedule section or the Revised Budget section blank if not applicable to your Scope Change request If you have questions, please email SSC's general email, Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title as Indicated on Original Award: |  | Decreasing Energy Usage in the INHS Fish Collection
| Original Award Date (or Semester/Year)*: |  | 17 Feb. 2023 | <*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.
| Amount Originally Awarded by SSC: |  | 171600
| Remaining Unspent Funds in Original Award**: |  | 165530 | <**NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Amount of Additional Funds Requested: |  | 0
| Expected Date of Project Completion: |  | 2025-10-17
| Date of This Scope Change Submission: |  | 2024-10-04
REVISED SCOPE & SCHEDULE
What is the revised plan for project implementation? Describe the key steps of the remaining project including the original estimated completion date for each item and the revised completion date as well as the required semester project reports and the required final project report. If there are new tasks not listed in the original award, indicate NEW for the original date. Be as detailed as possible so that the SSC can fully evaluate the merit of this Scope Change. Insert additional rows if necessary.
Task |  |  | Original Estimated Completion Date |  | REVISED Estimated Completion Date
solict and complete cost estimate form UI F & S |  |  | 16 weeks |  | 2024-10-30
solict bids from window insert vendors, solicit internal funds from PRI |  |  | 12 weeks |  | task has been completed
select window insert vendor removal of window AC units, installation of window inserts |  |  | 24 weeks |  | 2025-10-17
installation of outside AC units |  |  | 12 weeks |  | 2025-10-17
REVISED BUDGET
List all budget items for which funding is being requested under the appropriate category. Indicate whether it is a new item in the original budget or a revised item. Be as detailed as possible so that the SSC can fully evaluate the merit of this Scope Change. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
installation of window inserts |  | yes | 1000 | 12 | 12000
installation of external AC units |  | yes | 20000 | 6 | 120000
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  |  | 132000
Publicity & Communication
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  |  | 0
Personnel & Wages
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
removeal of window AC units and installation of replacement glass |  | no | 4000 | 6 | 24000
estimate of work by F & S |  | no | 15600 |  | 15600
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  |  | 39600
General Supplies & Other
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  |  | 0
|  |  |  | TOTAL REVISED BUDGET | 171600