## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Decreasing energy usage in the INHS Fish Collection
Total Amount Requested from SSC: | 171600
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
solicit and complete cost estimate from UI F & S | 16 weeks |  | 2023-04-30
solicit bids from window insert vendor, solicit internal funds from PRI | 12 weeks |  | 2023-07-31
select window insert vendor, removal of window AC units, installation of window inserts | 24 weeks |  | 2023-02-28
installation of outside AC units | 12 weeks |  | 2023-05-31
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
insulating window inserts | 10000 | 12 | 120000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 120000
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
removeal of window AC units and installation of replacement glass | 4000 | 6 | 24000
installation of window inserts | 1000 | 12 | 12000
estimate from F & S, estimated at 10% of project budget | 15600 | 1 | 15600
0
0
0
0
0
0
0
|  | Subtotal | 51600
Project Budget per F&S
n/a |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 171600
End of Application