## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Illini Formula Electric SiCVerter & Powertrain
Total Amount Requested from SSC: | 100000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
All hardware changes finalized (Schematics Needed)​ | 5 |  | 12/17/2022​
All IO tested, Start of FOC motor control code​ | 5 |  | 12/17/2022​
PCB Design finished, orders sent​ | 9 |  | 1/17/2023​
Fully assembled inverter​ | 15 |  | 3/1/2023​
Go kart endurance run ​ | 19 |  | 3/30/2023​
Updated Design ready to test​ | 31 |  | 7/1/2023​
HV Dyno test @ POETS or ECEB​ | 35 |  | 8/1/2023​
Updated Design ready to test – endurance dyno run ​ | 39 |  | 9/1/2023​
Car ready inverter set​ | 43 |  | 10/1/2023​
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
SiC MOSFET modules | 200 | 15 | 3000
Printed Circuit Boards | 80 | 15 | 1200
Microprocessors | 30 | 5 | 150
Encoder | 375 | 5 | 1875
Motors | 8000 | 5 | 40000
Assorted Electronics Components | 0.1 | 3000 | 300
Custom Water Cooling Block | 300 | 1 | 300
Custom Machined Motorsport Gears | 17000 | 1 | 17000
Machined Hub & Planet Carrier | 2000 | 5 | 10000
Machined Upright | 3200 | 4 | 12800
Gearbox Bearings | 500 | 5 | 2500
Brake Calipers | 800 | 4 | 3200
Brake System Master Cylinders | 1000 | 2 | 2000
Brake System Lining and Hardware | 500 | 1 | 500
Wire Harness Connectors and Supplies | 50 | 100 | 5000
|  | Subtotal | 99825
Publicity & Communication
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 99825
End of Application