## Supplemental Budget and Timelin
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | ADAPTHAUS, ILLINOIS SOLAR DECATHLON
Total Amount Requested from SSC: | 100000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
100% Construction Documentation | 8 |  | December 31st, 2019
Construction of modules in Skender's factory (start of shop drawings to fabrication) | 17 |  | March 31st, 2020
On site work | 10 |  | April 31st, 2020
Jury testing | 1 |  | May 15th, 2020
Module display in Washington DC | 3 |  | July 31st, 2020
Permanent Installation and Inspection in Champaign | 4 |  | August 31st, 2020
Final report submission to SSC | 4 |  | Sept 31st, 2020
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Foundations | 1.24 | 1800 | 2232
Superstructure (Floor and roof construction) | 72.03 | 1800 | 129654
Exterior Closure | 26.23 | 1800 | 47214
Roofing | 10.026 | 1800 | 18046.8
Interior Construction | 1.035 | 1800 | 1863
Interior Finishes | 23.01 | 1800 | 41418
Plumbing | 9.38 | 1800 | 16884
Mechanical | 29.18 | 1800 | 52524
Fire Protection | 0.41 | 1800 | 738
Electrical | 11.77 | 1800 | 21186
Equipment | 3.32 | 1800 | 5976
Furnishings | 11.22 | 1800 | 20196
Site Preparation | 1.71 | 1800 | 3078
Site Improvement | 2.76 | 1800 | 4968
Site Electrical Utilities | 1.58 | 1800 | 2844
Logistics (Transportation of Modules from Chicago to Champaign) | 3300 | 3 | 9900
Logistics (Transportation of Modules from Champaign to DC and back to Champaign) | 16500 | 2 | 33000
Setting of modules on site | 6000 | 4 | 24000
|  | Subtotal | 435721.8
Note: This breakdown is based on RS Means along with Skender's cost estimate for fabrication of modules in their factory.
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 435721.8
End of Application
Note on B44: Akash Jain: This cost estimate is based on RS Means. Fabrication of modules in factory is going to cost roughtly $150/SF which amounts to $237,000. The remaining cost would be for materials and labor on site and for transportation of modules.
Note on D61: Akash Jain: One way cost is $16,500
Note on E61: Akash Jain: 2 implies the cost for transportation of 1 module from Champaign to DC and back to Champaign

## Detail Construction Breakdown
| 2019-11-05 |  |  |  |  | NOTE TO ALL TEAM ESTIMATORS
| AdaptHaus |  |  |  |  | COLUMNS H, I, AND J CONTAIN FORMULAS
| University of Illinois at Urbana-Champaign |  |  |  |  | PLEASE DO NOT EDIT, MOVE, OR DELETE THEM!
75%
| Champaign, IL | [5 empty] | GFA | 1800 | Measure to the outer dimensions of floor plan. Building only (do not include decks, porches, patios, etc.)
CSI |  |  |  |  | UNIT | EST'D | SUB | TOTAL
CODE | DESCRIPTION |  | QTY | UNIT | COST | COST | TOTAL | COST
| A10 | FOUNDATIONS
| A1010 | STANDARD FOUNDATIONS
|  | ISOLATED FOOTING | 6.82 | CY | 6.82 | 46.5124
|  | CONTINUOUS FROST WALL | 41.11 | CY | 41.11 | 1690.0321
|  | CONTINUOUS FOOTING | 12.52 | CY | 12.52 | 156.7504
|  | 2FT x 150 FT x 60MIL VAPOR BARRIER | 24 | Sq. | 14.38 | 345.12
|  | SUBTOTAL |  |  |  |  | 2238.4149
| A1020 | SPECIAL FOUNDATIONS
|  | SUBTOTAL |  |  |  |  | 0
| A1030 | SLAB ON GRADE
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - FOUNDATIONS | [6 empty] | 2238.4149
| A20 | BASEMENT
| A2010 | BASEMENT EXCAVATION
|  | SUBTOTAL |  |  |  |  | 0
| A2020 | BASEMENT WALLS
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - BASEMENT CONSTRUCTION | [6 empty] | 0
| B10 | SUPERSTRUCTURE
| B1010 | FLOOR CONSTRUCTION
|  | 600S162-68 FLOOR JOIST BLOCKING | 60 | FT | 12.35 | 741
|  | 800S200-68 FLOOR JOIST | 800 | FT | 15.2 | 12160
|  | HSS8X4X1/4 FLOOR RIM JOIST | 26.4167 | EA (12') | 576 | 15216
|  | 350S200-54 STUD | 1668 | FT | 10.37 | 17297.16
|  | 350T150-54 STIFFENER | 140 | FT | 5.03 | 704.2
|  | 3/4" STRUCTURAL CONCRETE PANEL | 1800 | SF | 10.88 | 19584
|  | 350T162-54 BRACING CHANNEL | 395 | FT | 2.07 | 817.65
|  | 350T150-54 TRACK | 775 | FT | 2.52 | 1953
|  | SBR/R43 BRIDGING | 226 | FT | 6.3 | 1423.8
|  | 350S162-33 INTERIOR STUD | 539.4 | FT |  | 0
|  | LSSC4.25 CLIP ANGLE CONNECTOR | 135 | COUNT | 1.725 | 232.875
|  | SSC4.25 CLIP ANGLE CONNECTOR | 58 | COUNT | 1.947 | 112.926
|  | LSFC2.25 CLIP ANGLE CONNECTOR | 44 | COUNT | 0.69 | 30.36
|  | 2x8 TIMBER STUD, DOUGLAS FIR, SELECT STRUC, | 1314.78 | FT | 0.5 | 657.39
|  | 6X8 TIMBER STUD, DOUGLAS FIR, SELECT STRUC | 204.98 | FT | 3 | 614.94
|  | 1"X4" DECK BOARDS | 898.57 | SF | 3.1 | 2785.567
|  | ABU66SS POST BASE | 46 | COUNT | 20.78 | 955.88
|  | LUC66SS INTERIOR HANGER** | 390 | COUNT | 2.68 | 1045.2
|  | BC6SS POST CAP | 46 | COUNT | 14.35 | 660.1
|  | Exterior Deck Finish: Reclaimed wooden paneling Shade: Sundance White, Size 5 3/4" x 8" | 1110 | SF | 11.06 | 12276.6
|  | SUBTOTAL |  |  |  |  | 89268.648
| B1020 | ROOF CONSTRUCTION
|  | 350S162-68 ROOF JOIST BLOCKING | 60 | FT | 12.35 | 741
|  | 600S200-68 ROOF JOIST | 822 | FT | 15.2 | 12494.4
|  | 600T200-97 ROOF RIM JOIST | 304 | FT | 24.9 | 7569.6
|  | 3/4" STRUCTURAL CONCRETE PANEL | 1800 | SF | 10.88 | 19584
|  | SUBTOTAL |  |  |  |  | 40389
| TOTAL - SUPERSTRUCTURE | [6 empty] | 129657.648
| B20 | EXTERIOR CLOSURE
| B2010 | EXTERIOR WALLS
|  | Exterior Wall Cladding: Reclaimed Barn Wood Paneling Shade: Grey | 1232 | SF | 12.63 | 15560.16
|  | Exterior Wall Cladding: Reclaimed Barn Wood Paneling Shade: White | 521 | SF | 12.63 | 6580.23
|  | 2.5"x4'x8' POLYISO RIGID INSULATION PANEL | 4032 | SF | 1.3 | 5241.6
|  | 5" BLIND FASTENER | 1008 | ea | 0 | 0
|  | CLOSE-CELL SPRAYED FOAM | 2855 | Cubic FT |  | 0
|  | FLUID-APPLIED WEATHER-RESISTIVE BARRIER | 5 | ea | 350 | 1750
|  | LIQUID FLASHING | 24 | ea | 8.95 | 214.8
|  | 3/4" STRUCTURAL CONCRETE PANEL | 636 | SF | 10.88 | 6919.68
|  | 3/8" OSB Sheathing | 5355 | SF | 0.24 | 1285.2
|  | SUBTOTAL |  |  |  |  | 37551.67
| B2020 | EXTERIOR WINDOWS
|  | 4' X 4.5' Fiberglass Sliding Window Pella Impervia Series | 7 | ea | 190 | 1330
|  | 4' X 3.5' Fiberglass Sliding Window Pella Impervia Series | 1 | ea | 190 | 190
|  | 4' X 2' Fiberglass Fixed Window Pella Impervia Series | 4 | ea | 127
|  | 2' X 4.5' Fiberglass Fixed Window Pella Impervia Series | 5 | ea | 127 | 635
|  | 2' X 2' Fiberglass Fixed Window Pella Impervia Series | 2 | ea | 127 | 254
|  | SUBTOTAL |  |  |  |  | 2409
| B2030 | EXTERIOR DOORS
|  | Smart Door Lock, Amazon Alexa | 2 | ea | 229 | 458
|  | 3'-6" X 7' Fiberglass Framed Glass Hinged Door Pella Architect Series | 4 | ea | 1697 | 6788
|  | SUBTOTAL |  |  |  |  | 7246
| TOTAL - EXTERIOR CLOSURE | [6 empty] | 47206.67
| B30 | ROOFING
| B3010 | ROOF COVERINGS
|  | Exterior Roof Finish EPDM Membrane | 17.4 | Sq | 1.5 | 26.1
|  | 5/8"x4'x8' SECUROCK® BRAND ULTRALIGHT GLASS-MAT ROOF BOARD | 1920 | SF | 4.22 | 8102.4
|  | 2.5"x4'x8' POLYISO RIGID INSULATION PANEL | 7872 | SF | 1.26 | 9918.72
|  | FASTENER | 480 | ea |  | 0
|  | SUBTOTAL |  |  |  |  | 18047.22
| B3020 | ROOF OPENINGS
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - ROOFING | [6 empty] | 18047.22
| C10 | INTERIOR CONSTRUCTION
| C1010 | PARTITIONS
|  | SUBTOTAL |  |  |  |  | 0
| C1020 | INTERIOR DOORS
|  | 3' X 7' Wooden Flushed Door Pella Architect Series | 6 | ea | 310.5 | 1863
|  | SUBTOTAL |  |  |  |  | 1863
| C1030 | FITTINGS
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - INTERIOR CONSTRUCTION | [6 empty] | 1863
| C20 | STAIRCASES
| C2010 | STAIR CONSTRUCTION
|  | SUBTOTAL |  |  |  |  | 0
| C2020 | STAIR FINISHES
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - STAIRCASES | [6 empty] | 0
| C30 | INTERIOR FINISHES
| C3010 | WALL FINISHES
|  | Interior Wall cladding:White Paint Eggshell White Latex Paint with no VOC | 2785 | SF | 1.93 | 5375.05
|  | Interior Wall Cladding Tile: Porcelain Tile Type: Sculpture, 12 x 24 White | 539 | SF | 14.17 | 7637.63
|  | SUBTOTAL |  |  |  |  | 13012.68
| C3020 | FLOOR FINISHES
|  | Interior Floor Finish: Hardwood Flooring Shade: Oak Limestone | 803 | SF | 12.46 | 10005.38
|  | Interior Floor Finish: Cork Flooring- Nova New Dimensions Plank Shade: Grey | 545 | SF | 5.16 | 2812.2
|  | Interior Floor Finish Tile: Porcelain Tile Sculpture, 12 x 24 White | 132 | SF | 15.5 | 2046
|  | SUBTOTAL |  |  |  |  | 14863.58
| C3030 | CEILING FINISHES
|  | Interior Ceiling Finish: White Paint Eggshell White Latex Paint with no VOC | 1590 | SF | 2.21 | 3513.9
|  | Cabinetry: Oak Laminate Shade: Planked Raw Oak | 1200 | SF | 8.35 | 10020
|  | SUBTOTAL |  |  |  |  | 13533.9
| TOTAL - INTERIOR FINISHES | [6 empty] | 41410.16
| D10 | CONVEYING
| D1010 | ELEVATORS & LIFTS
|  | SUBTOTAL |  |  |  |  | 0
| D1020 | ESCALATORS & MOVING WALKWAYS
|  | SUBTOTAL |  |  |  |  | 0
| D1090 | OTHER CONVEYING SYSTEMS
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - CONVEYING SYSTEMS | [6 empty] | 0
| D20 | PLUMBING
| D2010 | PLUMBING FIXTURES
|  | Kitchen Faucet | 1 | Ea. | 171 | 171
|  | Kitchen Sink | 1 | Ea. | 410 | 410
|  | Shower Arm | 2 | Ea. | 126 | 252
|  | Bathroom Sink | 2 | Ea. | 276 | 552
|  | Glass Medicine Cabinet | 2 | Ea. | 211 | 422
|  | Hand Towel Bar | 2 | Ea. | 23 | 46
|  | Towel Bar | 2 | Ea. | 32 | 64
|  | Toilet Tissue Holder | 2 | Ea. | 24.2 | 48.4
|  | Glass Shelf | 2 | Ea. | 85.85 | 171.7
|  | Shower Door | 2 | Ea. | 530 | 1060
|  | Shower Drain | 2 | Ea. | 92 | 184
|  | Grab Bar | 8 | Ea. | 241.8 | 1934.4
|  | Bathroom Shower Head | 2 | Ea. | 285 | 818
|  | Bathroom Faucet | 2 | Ea. | 151 | 401
|  | Bathroom Composting Toilet | 2 | Ea. | 1000 | 2336
|  | SUBTOTAL |  |  |  |  | 8870.5
| D2020 | DOMESTIC WATER DISTRIBUTION
|  | Domestic hot/cold, 100 ft PEX Piping 1/2" | 3 | Ea. | 144.5 | 433.5
|  | Domestic hot/cold, 100 ft PEX Piping 1" | 2 | Ea. | 12.5 | 25
|  | Domestic hot/cold, 100 ft PEX Piping 3/8" | 2 | Ea. | 69.7 | 139.4
|  | Domestic hot/cold, 100 ft PEX Piping 1/2" | 2 | Ea. | 98.5 | 197
|  | Domestic hot/cold, 100 ft PEX Piping 3/4" | 2 | Ea. | 75.4 | 150.8
|  | PEX .5" elbow fitting | 25 | Ea. | 8 | 200
|  | PEX .5" Tee fitting | 9 | Ea. | 11 | 99
|  | PEX .5" Pipe hangar 10 pack | 3 | Ea. | 5 | 15
|  | Thermostatic mixing valve .5" | 4 | Ea. | 66 | 264
|  | Thermostatic mixing valve 3/8" | 2 | Ea. | 96 | 192
|  | 1" to 3/4" adaptor sharkbite PEX | 2 | Ea. | 15 | 30
|  | 3/4" to .5" adaptor sharkbite PEX | 2 | Ea. | 9 | 18
|  | 25 ft Pipe Insulation | 10 | Ea. | 7.4 | 74
|  | EcoSmart 27 kW 4 GPM | 1 | Ea. | 700 | 700
|  | PEX Sharkbite water heater connection | 1 | Ea. | 110 | 110
|  | Backflow Check for Water Main Double Check Valve Assembly | 1 | Ea. | 196 | 196
|  | PVC 1.5" to 2" | 2 | Ea. | 2 | 4
|  | PVC 2" to 3" | 1 | Ea. | 4 | 4
|  | PVC elbow fitting 1.5" | 17 | Ea. | 2.5 | 42.5
|  | PVC tee fitting 1.5" | 17 | Ea. | 3 | 51
|  | 4 Port Multiport Tee | 2 | Ea. | 18 | 36
|  | 3 Port Multiport Tee | 3 | Ea. | 33 | 99
|  | Ecocirc Pump | 3 | Ea. | 7 | 21
|  | SUBTOTAL |  |  |  |  | 3101.2
| D2030 | SANITARY WASTE
|  | Vent/Sanitary, 100 ft PEX Piping 1" 1/4" | 2 | Ea. | 126.31 | 252.62
|  | Vent/Sanitary, 100 ft PEX Piping 1" 1/2" | 2 | Ea. | 61.72 | 123.44
|  | Vent/Sanitary, 100 ft PEX Piping 2" | 1 | Ea. | 15.94 | 15.94
|  | Vent/Sanitary, 100 ft PEX Piping 2" 1/2" | 1 | Ea. | 5.56 | 5.56
|  | Sanitary, 10ft PVC Schedule 40 2" | 5 | Ea. | 55.1 | 275.5
|  | Sanitary, 10FT PVC Schedule 40 2.5" | 2 | Ea. | 31 | 62
|  | Venting, 5ft PVC Schedule 40 1.5" | 40 | Ea. | 78.25 | 3130
|  | Venting P Trap | 8 | Ea. | 7 | 56
|  | SUBTOTAL |  |  |  |  | 3921.06
| D2040 | RAIN WATER DRAINAGE
|  | Rainwater Collection System Aluminum Gutters 4inx10 ft | 30 | EACH | 11.72 | 351.6
|  | Rainwater Collection System Aluminum End with Oval Drop | 4 | EACH | 7.74 | 30.96
|  | Rainwater Collection System Aluminum Outside Gutter Mitre | 4 | EACH | 16.15 | 64.6
|  | Rainwater Collection System Aluminum Downspout 3inx4inx10ft | 8 | EACH | 16.32 | 130.56
|  | Rainwater Collection System Downspout Adapter | 4 | EACH | 8.64 | 34.56
|  | SUBTOTAL |  |  |  |  | 612.28
| D2090 | OTHER PLUMBING SYSTEMS
|  | Greywater Irrigation System, 10 ft Greywater Piping- PVC 3 in | 1 | Ea. | 13 | 13
|  | Greywater Irrigation System, 10 ft Greywater Piping- PVC 2 in | 1 | Ea. | 6.5 | 6.5
|  | Greywater Irrigation System, 2 ft Greywater Piping- PVC 3/4 in | 1 | Ea. | 11.2 | 11.2
|  | Greywater Irrigation System, 10 ft Greywater Piping- Sharkbite PEX 3/4 in | 60 | Ea. | 3 | 180
|  | 3/4" PEX sharkbite (100 ft. length) | 1 | Ea. | 49 | 49
|  | 3/4" PEX 45 degree elbow fitting | 2 | Ea. | 17 | 34
|  | 3/4" PVC to PEX sharkbite connection | 4 | Ea. | 12 | 48
|  | PVC 3" to 2" | 4 | Ea. | 2 | 8
|  | PVC 2" to 3/4" | 4 | Ea. | 1 | 4
|  | PVC 4" to 2" | 4 | Ea. | 6 | 24
|  | SUBTOTAL |  |  |  |  | 377.7
| TOTAL - PLUMBING | [6 empty] | 16882.74
| D30 | MECHANICAL
| D3010 | ENERGY SUPPLY
|  | Amazon Smart Plug | 10 | Ea. | 25 | 250
|  | Solar Panels | 29 | Ea. | 1000 | 29000
|  | Solar Edge Inverter | 1 | Ea. | 2000 | 2000
|  | Battery Storage | 1 | Ea. | 9800 | 9800
|  | MPPT Solar Charger Controller- Solar Panel Battery Regulator LCD Display with Dual USB Port Display 12V/24V Safe Protection(70A) | 1 | Ea. | 56.09 | 56.09
|  | SUBTOTAL |  |  |  |  | 41106.09
| D3020 | HEAT GENERATING SYSTEMS
|  | SUZ-KA12NA2 OUTDOOR UNIT | 1 | ea | 1549 | 1549
|  | SUBTOTAL |  |  |  |  | 1549
| D3030 | COOLING GENERATING SYSTEMS
|  | PEAD-A12AA7 DUCTED INDOOR UNIT | 1 | ea | 1387.25 | 1387.25
|  | CERV2 | 1 | ea | 5027.5 | 5027.5
|  | Broan-NuTone AE80SL InVent Energy Star Certified Humidity Sensing Fan with LED Light, 80 CFM 0.8 Sones, White | 2 | ea | 191.97 | 383.94
|  | Broan ULTRA GREEN™ - 50 CFM - High-Efficiency Bathroom Exhaust Fan - 4" or 6" Duct | 1 | ea | 182 | 182
|  | SUBTOTAL |  |  |  |  | 6980.69
| D3040 | DISTRIBUTION SYSTEMS
|  | Ducts | 120 | LF | 19.64 | 2356.8
|  | SUBTOTAL |  |  |  |  | 2356.8
| D3050 | TERMINAL & PACKAGE UNITS
|  | SUBTOTAL |  |  |  |  | 0
| D3060 | CONTROLS & INSTRUMENTATION
|  | Thermostat Amazon Alexa, Google Assistant, Energy Star 7.25" x 3" x 9" | 1 | ea | 160 | 160
|  | 1/4” x 3/8” 25 ft. Mini Split Line Set | 1 | ea | 117.5 | 117.5
|  | Mitsubihsi Controller | 1 | ea | 247.95 | 247.95
|  | SUBTOTAL |  |  |  |  | 525.45
| D3070 | SYSTEMS TESTING & BALANCING
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - HVAC | [6 empty] | 52518.03
| D40 | FIRE PROTECTION
| D4010 | SPRINKLERS
|  | SUBTOTAL |  |  |  |  | 0
| D4020 | STANDPIPES
|  | SUBTOTAL |  |  |  |  | 0
| D4030 | FIRE PROTECTION SPECIALTIES
|  | Fire Alarms | 7 | ea | 106.5 | 745.5
|  | SUBTOTAL |  |  |  |  | 745.5
| TOTAL - FIRE PROTECTION | [6 empty] | 745.5
| D50 | ELECTRICAL
| D5010 | ELECTRICAL SERVICE & DISTRIBUTION
|  | 10 guage AWG Cabling | 15 | Ft. | 0.3 | 4.5
|  | Disconnect Switches (AC and DC) | 1 | Ea. | 141.23 | 141.23
|  | Main Breaker Panel | 1 | Ea. | 214.65 | 214.65
|  | SUBTOTAL |  |  |  |  | 360.38
| D5020 | LIGHTING & BRANCH WIRING
|  | Archetype 18" Outdoor Wall Sconce 3000K | 6 | Ea. | 245.5 | 1473
|  | Chamber Post Mount 3000K | 8 | Ea. | 313 | 2504
|  | 1" INGROUND - ROUND | 6 | Ea. | 245.5 | 1473
|  | Blok Horizontal Wall Sconce 12" Wall Sconce 3000K | 3 | Ea. | 345.5 | 1036.5
|  | Caliber 10'' Pendant 3000K | 2 | Ea. | 256.5 | 513
|  | Equation Bathroom Sconce 3000K | 2 | Ea. | 85.5 | 171
|  | InvisiLED® Pro 2 24V LED Tape Light | 10 | Ea. | 453.5 | 4535
|  | Klein Wall Light 3000K | 3 | Ea. | 125.5 | 376.5
|  | Oculux 2" 11W Open Reflector Round | 22 | Ea. | 356.5 | 7843
|  | Vornado 7'' Single Pendant 3000K | 1 | Ea. | 353.5 | 353.5
|  | GLO Ceiling and Wall Mount | 2 | Ea. | 85.5 | 171
|  | Metro Ceiling and Wall Mount | 3 | Ea. | 125.5 | 376.5
|  | SUBTOTAL |  |  |  |  | 20826
| D5030 | COMMUNICATIONS & SECURITY
|  | SUBTOTAL |  |  |  |  | 0
| D5090 | OTHER ELECTRICAL SYSTEMS
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - ELECTRICAL | [6 empty] | 21186.38
| E10 | EQUIPMENT
| E1010 | COMMERCIAL EQUIPMENT
|  | Security System Amazon Alexa (10 Piece Kit), 2.7watts | 1 | ea | 329 | 329
|  | SUBTOTAL |  |  |  |  | 329
| E1020 | INSTITUTIONAL EQUIPMENT
|  | TV Amazon Alexa, Google Assistant, size 55" | 1 | ea | 430 | 430
|  | Samsung SmartThings Wifi Mesh Router Range Extender SmartThings Hub Functionality Whole-Home WiFi Coverage - Zigbee, Z-Wave, Cloud to Cloud Protocols - White (3 Pack) - ET-WV525KWEGUS | 1 | ea | 279.99
|  | Laptop 15.6" Energy Star | 1 | ea | 320
|  | SUBTOTAL |  |  |  |  | 430
| E1030 | VEHICULAR EQUIPMENT
|  | SUBTOTAL |  |  |  |  | 0
| E1090 | OTHER EQUIPMENT
|  | Refrigerator Amazon Alexa, Google Assistant,Energy Star, size 35 7/8" x 31 13/16" x 70 1/3" | 1 | ea | 1527 | 1527
|  | Microwave Amazon Alexa,scan-to-cook technology, size 19" x 14 1/2" x 11 1/2", 900 watts=0.9kw | 1 | ea | 145 | 145
|  | Stove Amazon Alexa, Google Assistant, Nest, size 29 7/8" x 28" x 47", 208V,40 amp | 1 | ea | 1450 | 1450
|  | Dishwasher Amazon Alexa, Google Assistant, Energy Star, size 23 3/4" x 24 5/8" x 33 5/8", 258 kwh per year | 1 | ea | 700 | 700
|  | Washer and 14-Cycle Electric Dryer Combo 2.3 Cu. Ft. Amazon Alexa, Google Assistant | 1 | ea | 1400 | 1400
|  | SUBTOTAL |  |  |  |  | 5222
| TOTAL - EQUIPMENT | [6 empty] | 5981
| E20 | FURNISHINGS
| E2010 | FIXED FURNISHINGS
|  | Kitchen cabinetry | 50 | SF | 80 | 4000
|  | Kitchen Counter: Quartz Shade: White, Counter Size: 28" x 18' | 30 | SF | 90 | 2700
|  | Kitchen Island | 1 | Ea. | 250 | 250
|  | Tango-Sectional- Convertible sofa-bed | 1 | Ea. | 1200 | 1200
|  | Passo- Transformable Coffee Table | 1 | Ea. | 300 | 300
|  | Glam Ottoman | 1 | Ea. | 200 | 200
|  | Caravela Barstool | 3 | Ea. | 150 | 450
|  | Discus Table | 2 | Ea. | 150 | 300
|  | Stockholm Sideboard | 1 | Ea. | 200 | 200
|  | Ark Bed +Mattress | 1 | Ea. | 700 | 700
|  | Burr Accent Chair | 1 | Ea. | 350 | 350
|  | Voya Coffee Table | 1 | Ea. | 250 | 250
|  | Full height cabinet | 1 | Ea. | 1000 | 1000
|  | Bunk Bed + 2 mattresses | 1 | Ea. | 1000 | 1000
|  | Pedestal storage | 1 | Ea. | 1000 | 1000
|  | Pigeonholes | 6 | Ea. | 300 | 1800
|  | Passo- Transformable Coffee Table | 1 | Ea. | 300 | 300
|  | Penelope-Transformable Bed-workstation | 2 | Ea. | 1000 | 2000
|  | Transforming Wall mounted Table | 1 | Ea. | 250 | 250
|  | Transforming Office | 1 | Ea. | 1000 | 1000
|  | Banquette seating | 1 | Ea. | 750 | 750
|  | Study desk | 1 | Ea. | 200 | 200
|  | SUBTOTAL |  |  |  |  | 20200
| E2020 | MOVABLE FURNISHINGS
|  | Smart Curtain Rod, Amazon Alexa |  | ea | 279
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - FURNISHINGS | [6 empty] | 20200
| F10 | SPECIAL CONSTRUCTION
| F1010 | SPECIAL STRUCTURES
|  | SUBTOTAL |  |  |  |  | 0
| F1020 | INTEGRATED CONSTRUCTION
|  | SUBTOTAL |  |  |  |  | 0
| F1030 | SPECIAL CONSTRUCTION SYSTEMS
|  | SUBTOTAL |  |  |  |  | 0
| F1040 | SPECIAL FACILITIES
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - SPECIAL CONSTRUCTION | [6 empty] | 0
| F20 | SELECTIVE BUILDING DEMOLITION
| F2010 | BUILDING ELEMENTS DEMOLITION
|  | SUBTOTAL |  |  |  |  | 0
| F2020 | HAZARDOUS COMPONENTS ABATEMENT
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - SELECTIVE BUILDING DEMOLITION | [6 empty] | 0
| G10 | SITE PREPARATION
| G1010 | SITE CLEARING
|  | SUBTOTAL |  |  |  |  | 0
| G1020 | SITE DEMOLITION AND RELOCATION
|  | SUBTOTAL |  |  |  |  | 0
| G1030 | SITE EARTHWORK
|  | Grading, Rough Grading, Rough grade sites 1100-3000, skid steer & labor | 1 | EACH | 831 | 831
|  | Excavation and Fill, Bulk Bank Measure, Excavator, Hydrualic, crawler mtd, 1 C.Y. cap. = 100 C.Y./hr | 305 | BCY | 1.93 | 588.65
|  | Excavation and Fill, Backfill, By hand compaction in 12" layers hand tamp | 50 | LCY | 33.15 | 1657.5
|  | SUBTOTAL |  |  |  |  | 3077.15
| G1040 | HAZARDOUS WASTE REMEDIATION
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - SITE PREPARATION | [6 empty] | 3077.15
| G20 | SITE IMPROVEMENT
| G2010 | ROADWAYS
|  | SUBTOTAL |  |  |  |  | 0
| G2020 | PARKING LOTS
|  | SUBTOTAL |  |  |  |  | 0
| G2030 | PEDESTRIAN PAVING
|  | SUBTOTAL |  |  |  |  | 0
| G2040 | SITE DEVELOPMENT
|  | SUBTOTAL |  |  |  |  | 0
| G2050 | LANDSCAPING
|  | Rock-Pea Gravel 3/8" 1CY | 13.33 | CY | 8.5 | 113.305
|  | Leaf Mulch | 8.03 | CY | 17.85 | 143.3355
|  | 2 in. x 6 in. x 10 ft. #2 and Better Kiln-Dried Heat Treated Spruce-Pine-Fir Lumber | 8 | Ea. | 7.05 | 56.4
|  | #10 x 3 in. Philips Bugle-Head Coarse Thread Sharp Point Polymer Coated Exterior Screw | 2 | Ea. | 3.98 | 7.96
|  | Emerald Blue Phlox | 300 | C | 6.36 | 1908
|  | Little Bluestem | 130 | C | 6.36 | 826.8
|  | Beyond Blue - Blue Fescue | 130 | C | 7.16 | 930.8
|  | Vegetable Seed mix | 20 | Ea. | 5 | 100
|  | 25 lb. Tall Fescue Grass Seed | 2 | lbs | 71.83 | 143.66
|  | Composting Bins | 3 | Ea. | 245 | 735
|  | SUBTOTAL |  |  |  |  | 4965.2605
| TOTAL - SITE IMPROVEMENT | [6 empty] | 4965.2605
| G30 | SITE MECHANICAL UTILITIES
| G3010 | WATER SUPPLY
|  | SUBTOTAL |  |  |  |  | 0
| G3020 | SANITARY SEWER
|  | SUBTOTAL |  |  |  |  | 0
| G3030 | STORM SEWER
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - SITE MECHANICAL UTILITIES | [6 empty] | 0
| G40 | SITE ELECTRICAL UTILITIES
| G4010 | ELECTRICAL DISTRIBUTION
|  | Electrical Utility Transmission and Distribution, Electrical Underground Ducts and Manholes, Not including excavation and backfill, Underground duct, banks ready for concrete fill, min of 7.5" between conduits, center to center, PVC, type EB, 2 @ 2" diameter | 200 | LF | 4.99 | 998
|  | Excavation and Fill, Bulk Bank Measure, Excavator, Hydrualic, crawler mtd, 1 C.Y. cap. = 100 C.Y./hr | 100 | BCY | 1.93 | 193
|  | Excavation and Fill, Backfill, By hand compaction in 12" layers hand tamp | 50 | LCY | 33.15 | 1657.5
|  | SUBTOTAL |  |  |  |  | 2848.5
| G4020 | SITE LIGHTING
|  | SUBTOTAL |  |  |  |  | 0
| G4030 | SITE COMMUNICATION AND SECURITY
|  | SUBTOTAL |  |  |  |  | 0
| G4090 | OTHER SITE ELECTRICAL UTILITIES
|  | SUBTOTAL |  |  |  |  | 0
| TOTAL - SITE ELECTRICAL UTILITIES | [6 empty] | 2848.5
|  | TOTAL DIRECT COST (Trade Costs) | [5 empty] | 368827.6734
[6 empty] | 368827.6734 | 368827.6734 | 368827.6734 | These values should match the value shown in the TOTAL DIRECT COST (Trade Costs) line above