## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Green Labs Pilot Program
Total Amount Requested from SSC: | 11000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Securing funding and hiring of Green Labs Coordinator | TBD |  | 2018-06-15
Initial onboarding, establishment of Green Labs Steering Committee, and initial lab surveys | 6 months |  | 2018-12-15
Creation of Certified Green Lab Program 1.0, expanded surveys of campus labs culminating in initial report of lab conditions. | 6 months |  | 2019-06-15
Expansion of Certified Green Lab program, expansion of self-reporting efforts for labs, culminating in generation of final policy recommendations for program | 18 months |  | 2020-12-15
Follow-up on recommendations as able and wrap-up of pilot | 6 months |  | 2021-06-15
Please note: many outreach efforts will be ongoing throughout the full three years of the program, and do not have fixed start or end dates. They will continue for the duration of the pilot, or longer should campus funding be secured to continue the position.
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Student Interns for three years | 11000 | 1 | 11000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 11000
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 11000
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
If SSC is willing to contribute the intern costs for this three-year pilot program, the remaining funds will be covered via funds from the sales of the University of Illinois' Carbon Credits, and possible contributions from the related Vice Chancellor for Research units.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
A specific estimate will be hard to generate prior to a comprehensive audit of total lab energy and water consumption. However, a similar program at Harvard saved $200K-$250K and 300-350 metric tons of CO2 per year. One goal for this pilot is to demonstrate sufficient savings at the University of Illinois to justify continuation of the program and the Green Labs Coordinator position through campus funding.
End of Application