## Semester Project Report
SSC Budget and Timeline Form - Semester Project Report
The SSC Budget and Timeline Form - Semester Project Report must be completed and submitted every semester regarless of the original application type. This form requires a list of updated project timelines and milestones and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Native American House (NAH) Water Dispenser
| Original Award Date (or Semester/Year)*: | 2024-10-25 | (<*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.)
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): | 6296.5
| Total Expenses This Period**: | 2820 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: | 3476.5 | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Expected Date of Project Completion: | 2025-02-18
| Date of This Application Submission: | 2024-12-16
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the progress you have made on the project since your last semester report. Include start and end dates and % complete). Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the progress of this project. Insert additional rows if necessary.
Task |  |  | Start Date | End Date (or estimated) | % Complete
Water Dispenser
Purchase of water dispenser from iBuy |  |  | 2024-11-25 | 2024-11-25 | 100%
Water line installation at NAH (F+S) |  |  | 2024-11-25 | 2024-12-18 | 0%
Delivery and set-up of Brio Water Dispenser (Dependent on schedule of F+S) |  |  | 2024-11-25 | 2024-12-18 | 0%
Place SSC sticker logo on Water Dispenser |  |  | 2024-11-25 | 2025-01-25 | 0%
Water Bottle and Bento Boxes
Purchase and Delivery of I AM ON NATIVE LANDWater Bottles (design already completed and approved by Marketing + Communications) |  |  | 2025-01-08 | 2025-01-23 | 0%
Bento Box NAH Logo Design + Marketing/Communication Approval |  |  | 2025-01-08 | 2025-01-23 | 0%
Purchase and delivery to NAH of bento boxes with NAH logo |  |  | 2025-01-08 | 2025-01-23 | 0%
Place SSC stickers on water bottles + Bento Boxes |  |  | 2025-01-08 | 2025-01-23 | 0%
Dinner On Us (NAH program) give away evening of water bottles and bento boxes |  |  | 2025-02-18 | 2025-02-18 | 0%
SSC Stickers
Request logo or sticker design from SSC |  |  | 2024-11-25 | 2024-11-25 | 100%
Send sticker to print at Sticker Mule |  |  | 2025-01-08 | 2025-01-08 | 0%
Receive stickers from Sticker Mule |  |  | 2025-01-23 | 2025-01-23 | 0%
Reports
End of semester report |  |  | 2024-12-13 | 2024-12-16 | 100%
Final Project Report |  |  | 2025-02-01 | 2025-02-18 | 0%
EXPENSES
List all expenditures from this award made since the last submitted semester project report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  |  | Total Spent
Brio 4 Filter RO Water Dispenser (Purchased through iBuy) |  |  |  | 2820
Brio Water Filter Kit (4 filters in kit, 1-year provision of filtration) |  |  |  | 0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 2820
Publicity & Communication
Item |  |  |  | Total Spent
"Funded by Green Fund/SSC" branded stickers (2" x 2" circle from Sticker Mule) |  |  |  | 0
Funded by Green Fund/SSC Sticker for Water Dispenser (5" x 7") |  |  |  | 0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  |  |  | Total Spent
*All wages for moving water line and installation of water dispenser are covered by F+S budget items* |  |  |  | 0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  |  |  | Total Spent
I Am On Native Land Water Bottles |  |  |  | 0
Bento Boxes with Cutlery |  |  |  | 0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  | Total Spent
F+S Labor for moving waterline and installation of water dispenser |  |  |  | 0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  | 2820