## Scope Change
SSC Budget and Timeline Form - Scope Change
The SSC Budget and Timeline Form - Scope Change must be completed and submitted with the SSC Scope Change Application. This form requires information about the originally awarded project as well as detailed information about the requested changes to the project's scope. Leave the Revised Scope & Schedule section or the Revised Budget section blank if not applicable to your Scope Change request If you have questions, please email SSC's general email, Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title as Indicated on Original Award: |  | High Efficency EV Racecar
| Original Award Date (or Semester/Year)*: |  | November 21, 2024 | <*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.
| Amount Originally Awarded by SSC: |  | $107,724.87
| Remaining Unspent Funds in Original Award**: |  |  | <**NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Amount of NET Additional Funds Requested***: |  | 0 | <***Reflect new net funds requested as a result of this scope change ONLY. This is the amount of additional funds that will be transferred to the project if this Scope Change is approved.
Expected Date of Project Completion:
| Date of This Scope Change Submission: |  | April 21st 2024
REVISED SCOPE & SCHEDULE
What is the revised plan for project implementation? Describe the key steps of the remaining project including the original estimated completion date for each item and the revised completion date as well as the required semester project reports and the required final project report. If there are new tasks not listed in the original award, indicate NEW for the original date. Be as detailed as possible so that the SSC can fully evaluate the merit of this Scope Change. Insert additional rows if necessary.
Task |  |  | Original Estimated Completion Date |  | REVISED Estimated Completion Date
Car with regenerative braking Design |  |  | 2024-11-01
Manufacturing Plan for vehicle |  |  | 2024-12-14
Manufacting Vehicle |  |  | 2025-03-31
Testing Vehicle, validate designs and gather data |  |  | 2025-06-09
Compete With Vehicle at FSAE |  |  | Jun 14- 2025
Car with torque vectoring Designed |  |  | 2025-11-01
Manufacturing Plan for vehicle |  |  | 2025-12-14
Manufacting Vehicle |  |  | 2026-03-31
Testing Vehicle, validate designs and gather data |  |  | 2026-06-09
Compete With Vehicle at FSAE |  |  | Jun 14- 2026
REVISED BUDGET
List all budget items under the appropriate category. Indicate whether it is a new item or a revised or deleted item in the original budget. The revised budget should reflect the entire project budget being funded by SSC, not just the new/revised/deleted items. This will allow SSC to fully evaluate any requested changes to the overall project budget. Be as detailed as possible so that the SSC can fully evaluate the merit of this Scope Change. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | New, Revised, Deleted Item? | Cost Per Item | Quantity | Total
Motors and Motor Controllers |  |  | 33474.87 | 1 | 33474.87
High Efficiency Wheels |  | New | 500 | 4 | 2000
Printed Circuit Boards |  | Revised | 50 | 100 | 5000
Motorsports Machined Gears |  |  | 30000 | 1 | 30000
Electronic Components |  | Revised | 0.5 | 1290 | 645
Sensors |  | Revised | 500 | 16 | 8000
Live Telemetry Module |  |  | 600 | 1 | 600
Wire Harness Materials |  |  | 50 | 88 | 4400
Insulative Materials |  |  | 150 | 5 | 750
Low Voltage Battery |  |  | 500 | 2 | 1000
Freezer |  | New | 2000 | 1 | 2000
Machined Uprights |  | Revised | 18000 | 1 | 18000
Equipment & Construction Costs Subtotal |  |  |  |  | 105869.87
Publicity & Communication
Item |  | New, Revised, Deleted Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  |  | 0
Personnel & Wages
Item |  | New, Revised, Deleted Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  |  | 0
General Supplies & Other
Item |  | New, Revised, Deleted Item? | Cost Per Item | Quantity | Total
ExTech Milliohm Meter |  | Revised | 1855 | 1 | 1855
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  |  | 1855
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | New, Revised, Deleted Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  |  | 0
|  |  |  | TOTAL REVISED BUDGET | 107724.87