## Semester Project Report
SSC Budget and Timeline Form - Semester Project Report
The SSC Budget and Timeline Form - Semester Project Report must be completed and submitted every semester regarless of the original application type. This form requires a list of updated project timelines and milestones and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | UIUC Campus Wind Turbine Project
| Original Award Date (or Semester/Year)*: | Fall 2024 | (<*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.)
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): | 160000
| Total Expenses This Period**: | 150000 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: | 10000 | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Expected Date of Project Completion: | 2024-11-21
| Date of This Application Submission: | 2025-12-17
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the progress you have made on the project since your last semester report. Include start and end dates and % complete). Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the progress of this project. Insert additional rows if necessary.
Task |  |  | Start Date | End Date (or estimated) | % Complete
Design of Civil Infrastructure around the Wind turbine including fence and gravel road |  |  | 2024-10-01 | 2024-12-31 | 100%
Design of Electrical Infrastructure around the Wind Turbine to be able to connect the utility grid |  |  | 2024-10-01 | 2024-12-31 | 100%
Design of the Site Lighting |  |  | 2024-10-01 | 2024-12-31 | 100%
Construction Adminstration by a Illinois Licensed Professional |  |  | 2024-11-30 | 2025-03-31 | 100%
Evaluate options to restore local ecological system |  |  | 2024-11-30 | 2026-06-30 | 0%
Construction of the gravel road |  |  | 2025-03-31 | 2025-06-30 | 100%
Construction of the fences |  |  | 2025-03-31 | 2025-06-30 | 100%
Construction of the electrical connection between the trailor and the University Electric Pole |  |  | 2025-03-31 | 2025-06-30 | 100%
Site Lighting |  |  | 2025-06-30 | 2025-09-30 | 100%
Installation of the 20 kW Wind Turbine |  |  | 2025-03-31 | 2025-09-30 | 90%
Implement the most efficient and cost effective option to restore local ecological system |  |  | 2025-03-31 | 2026-09-30 | 0%
EXPENSES
List all expenditures from this award made since the last submitted semester project report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  |  | Total Spent
Design of the gravel road, fencing, protection and electrical connection to grid |  |  |  | 50000
Civil prework for the ground |  |  |  | 5000
Electrical work to connect the turbine to the grid |  |  |  | 50000
Installation of fencing, gateway, sight lighting, and protection system |  |  |  | 45000
Planting local prarie plants in an ecologically restorative way |  |  |  | 0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 150000
Publicity & Communication
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  | 150000