## Scope Change
SSC Budget and Timeline Form - Scope Change
The SSC Budget and Timeline Form - Scope Change must be completed and submitted with the SSC Scope Change Application. This form requires information about the originally awarded project as well as detailed information about the requested changes to the project's scope. Leave the Revised Scope & Schedule section or the Revised Budget section blank if not applicable to your Scope Change request If you have questions, please email SSC's general email, Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title as Indicated on Original Award: |  | Single-Day Campus-Wide Composting Events.
| Original Award Date (or Semester/Year)*: |  | 2024-11-21 | <*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.
| Amount Originally Awarded by SSC: |  | 7000
| Remaining Unspent Funds in Original Award**: |  | 7000 | <**NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Amount of Additional Funds Requested: |  | 0
| Expected Date of Project Completion: |  | 2025-12-01
| Date of This Scope Change Submission: |  | 2025-01-28
REVISED SCOPE & SCHEDULE
What is the revised plan for project implementation? Describe the key steps of the remaining project including the original estimated completion date for each item and the revised completion date as well as the required semester project reports and the required final project report. If there are new tasks not listed in the original award, indicate NEW for the original date. Be as detailed as possible so that the SSC can fully evaluate the merit of this Scope Change. Insert additional rows if necessary.
Task |  |  | Original Estimated Completion Date |  | REVISED Estimated Completion Date
Initial Planning & Partnership Discussion with WasteNot Compost |  |  | 9/31/2024 |  | 9/31/2024
Formal Meeting with UIUC Team & WasteNot Compost |  |  | 2024-09-30 |  | 2024-09-30
Receive Quote from WasteNot Compost and Finalize Logistics and Agreement |  |  | 2024-10-31 |  | 2024-10-31
Volunteer Recruitment and Training |  |  | 2025-02-28 |  | 2025-02-28
Set up Composting Stations at Men’s Big Ten Basketball Game |  |  | 2025-03-31 |  | REMOVED
Set up Composting Stations at Earth Day Sustainapalooza |  |  | 2025-04-23 |  | 2025-04-23
Post-Event Data Collection and Reporting |  |  | 2025-05-31 |  | 2025-05-31
Set up Composting Stations at Men’s Big Ten Basketball Game |  |  | ----- |  | Late August
Post-Event Data Collection and Reporting |  |  | ----- |  | 2025-12-01
REVISED BUDGET
List all budget items for which funding is being requested under the appropriate category. Indicate whether it is a new item in the original budget or a revised item. Be as detailed as possible so that the SSC can fully evaluate the merit of this Scope Change. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  |  | 0
Publicity & Communication
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  |  | 0
Personnel & Wages
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
Sustainapalooza: WasteNot Compost Transportation, Bins, Compost Tipping Fee & Volunteer Training |  | - | 4000 | 1 | 4000
New Student Welcome Lunch 2025: WasteNot Compost Transportation, Bins, Compost Tipping Fee & Volunteer Training |  | - | 3000 | 1 | 3000
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  |  | 7000
General Supplies & Other
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | New or Revised Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  |  | 0
|  |  |  | TOTAL REVISED BUDGET | 7000