## Application - Budget
SSC Budget and Timeline Form - New Application
The SSC Budget and Timeline Form - New Application must be completed and submitted with the SSC Funding Application - Step 1, SSC Funding Application - Step 2 and the SSC Funding Application - Student Led Under $10,00.00. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. *NOTE: The SSC is not able to fund every project in full for which we receive an application. If you wish to also present alternate, lower budget scenarios to guide the SSC in making decisions in case we cannot fully fund your project, you may complete the additional tabs in this document labeled "Applic-Alternate Budget 1" and "Applic-Alternate Budget 2". If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Building Sustainability Program Equipment Catalog
| Amount Requested from SSC*: | 23723.2 | (<*This field autopopulates based on your budget entries below. Do not edit.)
| Date of This Application Submission: | 2024-10-16
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  | Estimated Start Date |  | Estimated Completion Date
Step 1 Application completed |  | October 16th 2024
Step 1 vote |  | October 20th 2024
(If motion is successful)
Step 2 Application completed |  | November 8th 2024
Step 2 vote |  | November 17th 2024
(If motion is successful)
Accept Grant |  | November 18th 2024 |  | November 30th 2024
Create stand-alone CFOP |  | December 1st 2024 |  | December 31st 2024
Submit 3 quotes to purchasing to approve a purchase order |  | January 1st 2025 |  | January 15th 2025
Await confirmation and allow for delivery |  | February 1st 2025 |  | February 28th 2025
Assign Facilities and Services trailer storage permission and allow for SSC marketing as well as zero waste and recycling signage. |  | March 1st 2025 |  | March 15th 2025
| Have equipment ready for Earth Month | April 1st 2025
| Close out the project submit final reports | April
BUDGET
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total
2024 JOHN DEERE HPX615E GATOR |  | 16726.2 | 1 | 16726.2
5' X 10' Carry-On Utility Pipe Top Trailer |  | 2419 | 1 | 2419
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 19145.2
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
UIUC & SSC branding for Gator |  | 750 | 1 | 750
SSC and Zero Waste branding banners for cart |  | 150 | 4 | 600
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 1350
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
UIUC Parking Fee (1 Year) |  | 2228 | 1 | 2228
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 2228
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
UIUC I year maintanance (oil change, brakes) |  | 350 | 2 | 700
Structure to support banners on cart (F&S) |  | 300 | 1 | 300
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 1000
TOTAL PROJECT BUDGET |  |  |  | 23723.2