## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Reducing Water Waste in Talbot Laboratory
Total Amount Requested from SSC: | 80000
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
F&S to develop plans for chilled water connection | 5/1/2022 to 7/1/2022 (8 wks) |  | 2022-07-01
F&S submits plans for approval to EP Lab Director | 7/1/2022 to 7/8/2022 (1wk) |  | 2022-07-08
Site preparation: F&S and EP Lab personnel | 7/1/2022 to 7/22/2022 (3wks) |  | 2022-07-22
Project execution by F&S | 7/25/2022 to 8/1/2022 (1wk) |  | 2022-08-01
Project commissioning: F&S and EP Lab personnel | 8/1/2022 to 8/14/2022 (1wk) |  | 2022-08-14
Project monitoring and close-out: F&S | 8/8/2022 to 8/22/2022 (2 wks) |  | 2022-08-22
Project communication: F&S and AE department | 7/1/2022 to 9/1/2022 |  | 9/1/202
Final report |  |  | 2022-10-01
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
F&S Formal Quote | 1500 | 1 | 1500
F&S Costs to Connect to Building Chilled Water | 78500 | 1 | 78500
0
0
0
0
0
0
0
0
|  | Subtotal | 80000
General Supplies & Other
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 80000
End of Application