## Semester Project Report
SSC Budget and Timeline Form - Semester Project Report
The SSC Budget and Timeline Form - Semester Project Report must be completed and submitted every semester regardless of the original application type. This form requires a list of updated project timelines and milestones and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Steven S. Wymer Hall (Wymer Hall) Formerly the South Campus Center for Interdisciplinary Learning (SCCIL), renamed Steven S. Wymer Hall at the Board of Trustees meeting on March 30, 2023.
| Original Award Date (or Semester/Year)*: | Spring 2023 Fall 2023 Spring 2024 Fall 2024 | (<*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.)
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): | 500000
| Total Expenses This Period**: | 970000 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: | 0 | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Expected Date of Project Completion: | 2025-01-20
| Date of This Application Submission: | 2024-12-06
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the progress you have made on the project since your last semester report. Include start and end dates and % complete). Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the progress of this project. Insert additional rows if necessary.
Task |  |  | Start Date | End Date (or estimated) | % Complete
Ceremonial Groundbreaking |  |  |  | 2023-04-14 | 100%
Construction Start |  |  |  | 2023-05-08 | 100%
Geothermal Field - Contractor Mobilization |  |  |  | 2023-12-04 | 100%
Geothermal Field - Day 1 - Begin drilling operations |  |  |  | 2023-12-20 | 100%
Geothermal Field - Drill rigs demobilized - Drilling of 70 450' deep geothermal wells complete |  |  |  | 2024-02-23 | 100%
Geothermal Field - Continue geothermal well field underground connections to Wymer Hall |  |  |  | 2024-03-15 | 100%
Geothermal Field - Grade and Reseed (Remaining site restoration, including fence removal, contractor job trailer removal, etc. to occur spring 2025.) |  |  |  | spring 2024 | 90%
Substantial Completion (SC) |  |  |  | 2025-01-20
Auditorium Complete |  |  |  | 2025-02-28
Terrace, landscaping, remaining site work |  |  |  | 2025-05-01
Commissioning, Owner move-in, soft opening |  |  |  | spring/summer 2025
Final Report to SSC |  |  |  | 2025-05-01
First classes held |  |  |  | 2025-08-25
EXPENSES
List all expenditures from this award made since the last submitted semester project report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Contractor's Schedule of Values** | Total Billed to Date** | Total Spent
SB - Equipment |  | 2212412 | 1991170
*A&R - Geothermal Equipment and Install |  | 4331358.24
TOTAL - Geothermal Equipment and Install |  | 6543770.24
*A&R - Geothermal Field Only (included in above) The SSC is funding a portion of this line item. |  | 970000 | 970000 | 970000
Landscaping and Repair at Military Axis (estimated cost) |  | 55300
**Added columns to update information submitted spring 2025 for easier tracking.
Equipment & Construction Costs Subtotal |  |  |  | 970000
Publicity & Communication
Item |  |  |  | Total Spent
Digital Screens and SSC Cross-Promotion
SSC physical signage acknowledgement
Geothermal webstory on Gies Business webpage https://giesbusiness.illinois.edu/news/2024/01/03/wymer-hall-going-geothermal-to-enhance-sustainability
X (formerly Twitter) - also links to Gies webpage on Wymer https://x.com/giesbusiness/status/1854622012523639242
LinkedIn https://www.linkedin.com/posts/giesbusiness_its-looking-just-how-we-drew-it-up-check-activity-7262184926962229250-HgPG?utm_source=share&utm_medium=member_desktop
Instagram https://www.instagram.com/reel/DA8xAcuPIr8/?utm_source=ig_web_copy_link
X (formerly Twitter) https://x.com/giesbusiness/status/1833585010114498624
X (formerly Twitter) https://x.com/giesbusiness/status/1822021461298569726
Facebook https://www.facebook.com/giesbusiness/videos/921789646373936/?rdid=P2CNmFl8PssHI3iZ
Instagram https://www.instagram.com/p/C9NFDJDOjhW/?utm_source=ig_web_copy_link
X (formerly Twitter) https://x.com/giesbusiness/status/1807153791655133249
LinkedIn https://www.linkedin.com/posts/giesbusiness_taking-a-closer-look-at-a-one-of-a-kind-spot-activity-7211455812651601921-tiVM?utm_source=share&utm_medium=member_desktop
Facebook https://www.facebook.com/giesbusiness/posts/pfbid0yQ5pXU2nxc33b2wmVd3JoxBCu3JDk54qL8bkd5wzZuGZBnbnZ3MxDYfd2Y8tXnkJl
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  |  |  | Total Spent
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  |  |  | Total Spent
General Supplies & Other Subtotal |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  | Total Spent
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  | 970000