## Reallocated Budget
SSC Budget and Timeline Form - Scope Change
GENERAL PROJECT INFORMATION
| Project Title as Indicated on Original Award: | Illini Solar Car - Project D
| Original Award Date (or Semester/Year)*: | April 29th, 2025 | <*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.
| Amount Originally Awarded by SSC: | 129479
| Remaining Unspent Funds in Original Award**: | 115345.84 | <**NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Amount of NET Additional Funds Requested***: | 0 | <***Reflect new net funds requested as a result of this scope change ONLY. This is the amount of additional funds that will be transferred to the project if this Scope Change is approved.
| Expected Date of Project Completion: | 2026-03-20
| Date of This Scope Change Submission: | September 25th, 2025
REVISED BUDGET
The original budget is included on the second page of this spreadsheet. We highlighted the differences between the budgets.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total | Changes are highlighted
Roll Cage Welding |  | 580 | 1 | 580
Roll Cage Bending |  | 1000 | 1 | 1000
Roll Cage Metal Pipe |  | 1200 | 1 | 1200
Resin |  | 400 | 5 | 2000
Carbon Fiber |  | 500 | 12 | 6000
Metal Parts for Suspension |  | 100 | 60 | 6000
Prepreg |  | 1000 | 20 | 20000
Structual Chassis Foam |  | 1000 | 16 | 16000
Foam Core |  | 1000 | 1 | 1000
Nomex Core |  | 1000 | 1 | 1000
Honeycomb Core |  | 3000 | 1 | 3000
Motor and Motor Controller |  | 13900 | 1 | 13900
Battery Pack |  | 11499 | 1 | 11499
PCB Manufacturing |  | 500 | 26 | 13000
Suspension Manufacturing |  | 5500 | 1 | 5500
Steering Wheel Component |  | 1500 | 1 | 1500
Low-Voltage Electrical Components |  | 200 | 50 | 10000
Composites Components and Materials |  | 1000 | 11 | 11000
Aerodynamics testing and plastics |  | 1000 | 1 | 1000
Safety Materials (gloves, glasses, respirators) |  | 10 | 430 | 4300
Equipment & Construction Costs Subtotal |  |  |  | 129479
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL PROJECT BUDGET |  |  |  | 129479

## Original Budget
SSC Budget and Timeline Form - New Application
The SSC Budget and Timeline Form - New Application must be completed and submitted with the SSC Funding Application - Step 1, SSC Funding Application - Step 2 and the SSC Funding Application - Student Led Under $10,00.00. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. *NOTE: The SSC is not able to fund every project in full for which we receive an application. If you wish to also present alternate, lower budget scenarios to guide the SSC in making decisions in case we cannot fully fund your project, you may complete the additional tabs in this document labeled "Applic-Alternate Budget 1" and "Applic-Alternate Budget 2". If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Illini Solar Car - Project D
| Amount Requested from SSC*: | 129479 | (<*This field autopopulates based on your budget entries below. Do not edit.)
| Date of This Application Submission: | 2025-04-18
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  | Estimated Start Date |  | Estimated Completion Date
Plug Machining: Plug is sent off to be machined by external company to get smooth finish for plug shape. |  | 2/17/2025 |  | 5/26/2025
Machining & Waterjetting: Taking final designs of metal and sandwich panel components and performing machining opertions to achieve final parts. |  | 5/25/2025 |  | 10/24/2025
Mold Post-Processing: Sanding, surfacing and bondoing done on mold to clean up surface to be ready for laying up |  | 5/26/2025 |  | 9/15/2025
Battery Box Assembly: Assembling battery box components to create final installable battery box. |  | 5/26/2025 |  | 11/24/2025
Layups: Carbon fiber and fiberglass composites layup process to create lightweight structures. |  | 9/22/2025 |  | 11/24/2025
Mate Shell and Chassis: Joining finished shell laminates with finished chassis laminate/components to form final structural car body |  | 9/24/2025 |  | 10/20/2025
Electrical System Integration: Integration of electrical systems into car to allow full car functionality and enable driving car. |  | 10/20/2025 |  | 12/14/2025
Vinyl Wrap and Apply Logos: Laying down smooth vinyl wrap for aesthetic car exterior and smooth aero finish. Placing sponsor stickers and logos |  | 10/24/2025 |  | 12/14/2025
Testing and Fixing: Texting car through drive days and static and dynamic tests to ensure all car components perform as desired and to iron out issues before competition. |  | 1/21/2026 |  | 5/18/2026
Project Final Report |  | 2/15/2026 |  | 3/20/2026
BUDGET
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total
Roll Cage Welding |  | 580 | 1 | 580
Roll Cage Bending |  | 1000 | 1 | 1000
Roll Cage Metal Pipe |  | 1200 | 1 | 1200
Resin |  | 749.95 | 20 | 14999
Carbon Fiber |  | 500 | 20 | 10000
Metal Parts for Suspension |  | 100 | 60 | 6000
Prepreg |  | 1000 | 34 | 34000
Structual Chassis Foam |  | 1000 | 15 | 15000
Foam Core |  | 1000 | 1 | 1000
Nomex Core |  | 1000 | 1 | 1000
Honeycomb Core |  | 3000 | 1 | 3000
Motor and Motor Controller |  | 12000 | 1 | 12000
Battery Pack |  | 5700 | 1 | 5700
PCB Manufacturing |  | 500 | 30 | 15000
Suspension Manufacturing |  | 5500 | 1 | 5500
Steering Wheel Component |  | 1500 | 1 | 1500
Low-Voltage Electrical Components |  | 200 | 10 | 2000
Equipment & Construction Costs Subtotal |  |  |  | 129479
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL PROJECT BUDGET |  |  |  | 129479