## Application - Budget
SSC Budget and Timeline Form - New Application
The SSC Budget and Timeline Form - New Application must be completed and submitted with the SSC Funding Application - Step 2 and the SSC Funding Application - Student Led Under $10,00.00. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. *NOTE: The SSC is not able to fund every project in full for which we receive an application. If you wish to also present alternate, lower budget scenarios to guide the SSC in making decisions in case we cannot fully fund your project, you may complete the additional tabs in this document labeled "Applic-Alternate Budget 1" and "Applic-Alternate Budget 2". If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Power and Ventilation for shipping containers
| Amount Requested from SSC*: | 60511 | (<*This field autopopulates based on your budget entries below. Do not edit.)
| Date of This Application Submission: | 2025-04-14
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  | Estimated Start Date |  | Estimated Completion Date
Adding power to the shipping containers |  | 2025-05-15 |  | 2025-06-06
Install lights and ventilation system |  | 2025-06-09 |  | 2025-06-20
BUDGET
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 0
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
Electrical Shop - Install a 100-amp panel by Bicycle Storage Containers. Provide in each container (3) LED Light fixtures with a switch, (1) Power for exhaust fan (Fan by Sheet Metal Shop), (1) Duplex Outlet. All underground trenching provided by labors is included. |  | 39610 | 1 | 39610
Sheet Metal Shop - Purchase exhaust fan |  | 1000 | 7 | 7000
Sheet Metal Shop - Installation of fan. 2 men for one day for each container |  | 1200 | 7 | 8400
Contingency |  | 10% | 1 | 5501
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 60511
TOTAL PROJECT BUDGET |  |  |  | 60511

## Applic - Alternate Budget 1
SSC Budget and Timeline Form - New Application - Alternate Budget #1
The SSC Budget and Timeline Form - New Application - Alternate Budget #1 is an optional document that can be submitted with the original proposed budget for a new project. Complete this document if you wish to offer the SSC a reduced budget scenario in case they cannot fully fund your entire budget. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. Completion of this form does not guarantee funding. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
Project Title:
| Alternate Amount Requested from SSC*: |  | 0 | (<*This field autopopulates based on your budget entries below. Do not edit.)
Date of This Application Submission:
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include required semester project reports and the final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  |  | Estimated Start Date |  | Estimated Completion Date
ALTERNATE BUDGET #1
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  |  | 0
Publicity & Communication
Item |  | New Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  |  | 0
Personnel & Wages
Item |  | New Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  |  | 0
General Supplies & Other
Item |  | New Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | New Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  |  | 0
TOTAL PROJECT BUDGET |  |  |  |  | 0

## Applic - Alternate Budget 2
SSC Budget and Timeline Form - New Application - Alternate Budget #2
The SSC Budget and Timeline Form - New Application - Alternate Budget #2 is an optional document that can be submitted with the original proposed budget for a new project. Complete this document if you wish to offer the SSC a reduced budget scenario in case they cannot fully fund your entire budget. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. Completion of this form does not guarantee funding. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
Project Title:
| Alternate Amount Requested from SSC*: |  | 0 | (<*This field autopopulates based on your budget entries below. Do not edit.)
Date of This Application Submission:
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include required semester project reports and the final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  |  | Estimated Start Date |  | Estimated Completion Date
ALTERNATE BUDGET #1
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  |  | 0
Publicity & Communication
Item |  | New Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  |  | 0
Personnel & Wages
Item |  | New Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  |  | 0
General Supplies & Other
Item |  | New Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | New Item? | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  |  | 0
TOTAL PROJECT BUDGET |  |  |  |  | 0