## Semester Project Report
SSC Budget and Timeline Form - Semester Project Report
The SSC Budget and Timeline Form - Semester Project Report must be completed and submitted every semester regarless of the original application type. This form requires a list of updated project timelines and milestones and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Engineered renewable nuclease biocatalyst for degradation of antibiotic resistance genes from wastewater
| Original Award Date (or Semester/Year)*: | 45776 | (<*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.)
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): | 13848
| Total Expenses This Period**: | 2496.48 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: | 11352 | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Expected Date of Project Completion: | 2026-05-15
| Date of This Application Submission: | 2025-03-22
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the progress you have made on the project since your last semester report. Include start and end dates and % complete). Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the progress of this project. Insert additional rows if necessary.
Task |  |  | Start Date | End Date (or estimated) | % Complete | Note
We will collaborate with the financial advisor to purchase the genes and reagents listed in our budget (items 85-89). Once received, we will begin constructing the plasmids. |  |  | 2025-06-15 | 2025-08-15 | 30% | we purchased reagents for some experiments, more will be purchased depending on the research needs.
We will transform the verified plasmids (item 89) into the host yeast to express the target protein and generate the biocatalyst. Functional surface display will be confirmed through activity assays and immunofluorescence characterization using the reagents and materials listed in our budget (items 43, 90-95). |  |  | 2025-08-15 | 2025-10-15 | 75% | we have constructed active nuclease biocatalys. We need to confirm them using immunofluorescence characterization
If the surface display is unsuccessful, we will explore alternative enzyme candidates. This will require returning to the cloning process and evaluating the functionality of new enzyme candidates, following steps 1-2. |  |  | 2025-10-15 | 2025-11-15 | 100% | we have constructed active nuclease biocatalys. So this step is skipped
If the surface display is successful, we will assess the biocatalyst's robustness by testing its ability to degrade antibiotic resistance genes in secondary wastewater effluent, using a buffered solution as a control. If the biocatalyst exhibits significantly lower activity in wastewater compared to the buffer, we will explore enzyme mutants to enhance its stability and performance (item 96, steps 1, 2, 4). |  |  | 2025-11-15 | 2025-12-10 | 75% | We have tested its robustness in the secondary wastewater effluent, and it showed good activity. We need more characterization using clinically and environmentally relevant plsmids
At this stage, enzyme candidate screening is complete. Next, we will optimize the biocatalyst for practical applications by removing the ampicillin resistance gene from the plasmid (item 97). We will then perform the transformation and construct the biocatalyst for further characterization (steps 1-2). |  |  | 2025-12-10 | 2025-12-25 | 50% | This part is a bit tricky, and we are working on it. Meanwhile, we are integrating the display cassette into the host genome to generate a marker-free strain while simultaneously ensuring stable and robust gene expression.
EXPENSES
List all expenditures from this award made since the last submitted semester project report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  |  | Total Spent |  | Note
Fisherbrand™ Multi-Purpose Tube Rotators (for mixing during degradation experiments) |  |  |  | 0 |  | I found a good instrument for mixing, so I didi not purchase this.
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 0
Publicity & Communication
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  |  |  | Total Spent
Undergraduate 1 |  |  |  | 0 |  | The undergraduate mainly got some training for the first semester, so I did not pay for the undergraduate so far
Undergraduate 2 |  |  |  | 0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  |  |  | Total Spent
Different nuclease genes |  |  |  | 583
0
0
Restriction enzyme, ligase, polymerase, Dnase, primers |  |  |  | 597.15
Sequencing services |  |  |  | 120
Cell culture medium and other reagents |  |  |  | 999.45
Transformation assays |  |  |  | 196.88
0
0
0
General Supplies & Other Subtotal |  |  |  | 2496.48
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  | 2496.48