## Final Project Report
SSC Budget and Timeline Form - Final Project Report
The SSC Budget and Timeline Form - Final Project Report must be completed upon completion of a project OR upon expiration of an award, whichever comes first. This form requires a complete list of updated project timelines and milestones for the project and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Native American Heritage Month Speaker: Dr. Jessica Hernandez
| Original Award Date (or Semester/Year)*: | 2025-10-13 | <*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): | 9949.44
| Total Expenses This Period**: | 9662.86 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: | 286.58 | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Date of This Application Submission: | 2025-12-11
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the work you accomplished on the entire project. Include start and end dates and % complete). Be as detailed as possible so that the SSC can fully evaluate this project. Insert additional rows if necessary.
Task |  |  | Start Date | End Date (or estimated) | % Complete
Finalize SSC proposal and submit |  |  | 2025-08-01 | 2025-09-20 | 100%
Present to SSC Working Group |  |  | 2025-09-30 | 2025-09-30 | 100%
Procurement of sustainability-focused materials (e.g., reusable water bottles, bento boxes) |  |  | 2025-10-13 | 2025-11-13 | 100%
Promote event via socials and NAH newsletter |  |  | 2025-10-01 | 2025-11-04 | 100%
Host Community Welcome Event |  |  | 2025-11-04 | 2025-11-04 | 100%
Host Dinner on Us with Dr. Jessica Hernandez |  |  | 2025-11-04 | 2025-11-04 | 100%
Distribute bottles and bento boxes |  |  | 2025-11-04 | 2025-11-18 | 100%
Document and photograph events; gather student feedback |  |  | 2025-11-04 | 2025-11-04 | 100%
Submit final report to SSC |  |  | 2025-11-04 | 2025-12-09 | 100%
EXPENSES
List all expenditures from this award made since the last semester report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 0
Publicity & Communication
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  |  |  | Total Spent
Honorarium (Jessica Hernandez) |  |  |  | 5000
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 5000
General Supplies & Other
Item |  |  |  | Total Spent
Glass Water Bottles |  |  |  | 2620.36
Bento Boxes |  |  |  | 2042.5
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 4662.86
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  | 9662.86