## Application - Budget
SSC Budget and Timeline Form - New Application
The SSC Budget and Timeline Form - New Application must be completed and submitted with the SSC Funding Application - Step 1, SSC Funding Application - Step 2 and the SSC Funding Application - Student Led Under $10,00.00. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. *NOTE: The SSC is not able to fund every project in full for which we receive an application. If you wish to also present alternate, lower budget scenarios to guide the SSC in making decisions in case we cannot fully fund your project, you may complete the additional tabs in this document labeled "Applic-Alternate Budget 1" and "Applic-Alternate Budget 2". If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Uni High Native Prairie Garden
| Amount Requested from SSC*: | 33681.25 | (<*This field autopopulates based on your budget entries below. Do not edit.)
| Date of This Application Submission: | 2025-11-05
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  | Estimated Start Date |  | Estimated Completion Date
Initial approval of project by the Uni administration |  | 2024-04-15 |  | 2024-04-15
Formed a team of collaborators with faculty and staff from F & S, Illinois Extension, iSEE, and NRES. |  | 2024-05-25 |  | Ongoing
Complete a 4-week workshop series on pollinator garden design facilitated by staff from Illinois Extension. |  | 2025-09-04 |  | 2025-09-25
Finalize design and seek final approval of the garden from Uni administration. |  | 2025-09-04 |  | 2025-11-21
Notified as recipient of the PTA Youth Engagement Capacity Building grant ($5,000 towards this project) |  | 2025-11-05 |  | 2025-11-05
Present the project to the Architectural Review Committee (ARC) to seek their approval and finalize the memorandum of understanding with F&S. |  | 2025-12-01 |  | 2025-12-12
Submit work order to F & S and site preparation (date range reflecting possible wait time for proper weather conditions) |  | 2025-12-12 |  | 2026-03-15
Submit Progress Report for the Fall of 2025 |  | 2025-12-18 |  | 2025-12-18
Purchase of equipment and plants. |  | 2026-03-02 |  | 2026-04-17
Complete prairie planting alongside collaborators. |  | 2026-04-01 |  | 2026-05-18
Submit Progress Report for the Spring of 2026 |  | 2026-05-14 |  | 2026-05-14
Submit Final Report |  | 2026-10-30 |  | 2026-10-30
BUDGET
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total
Plant Plugs (Pizzo Nursery) |  | 0.5 | 12000 | 6000 | (number and plant species is currently being determined by students designing the garden)
Outdoor Bench Tables |  | 1000 | 6 | 6000
Benches |  | 675 | 5 | 3375
Tool shed |  | 9500 | 1 | 9500
Firepit |  | 275 | 1 | 275
Hose Reel Cart |  | 200 | 1 | 200
Commercial Hose |  | 85 | 2 | 170
B-hyve XD Smart Hose Timer |  | 60 | 2 | 120
Mulch (cubic yard) |  | 27 | 30 | 810
Rain Barrel |  | 170 | 2 | 340
Oscillating Sprinkler |  | 60 | 4 | 240
Equipment & Construction Costs Subtotal |  |  |  | 27030 |  | 27030 | 22030
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
None |  |  |  | 0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
None |  |  |  | 0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
Floral Shovel |  | 28 | 10 | 280
Field Rake |  | 100 | 5 | 500
Bow Rake |  | 30 | 5 | 150
Garden scissors |  | 20 | 10 | 200
Garden Bypass Loppers |  | 35 | 10 | 350
Gloves |  | 10 | 10 | 100
Buckets |  | 4.75 | 15 | 71.25
0
0
0
General Supplies & Other Subtotal |  |  |  | 1651.25
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
Site preparation |  | 1000 | 1 | 1000
F & S Site maintenance (2 years) |  | 2000 | 2 | 4000
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 5000
TOTAL PROJECT BUDGET |  |  |  | 33681.25

## Applic - Alternate Budget 1
SSC Budget and Timeline Form - New Application - Alternate Budget #1
The SSC Budget and Timeline Form - New Application - Alternate Budget #1 is an optional document that can be submitted with the original proposed budget for a new project. Complete this document if you wish to offer the SSC a reduced budget scenario in case they cannot fully fund your entire budget. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. Completion of this form does not guarantee funding. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Uni High Native Prairie Garden
| Alternate Amount Requested from SSC*: | 28683.5 | (<*This field autopopulates based on your budget entries below. Do not edit.)
| Date of This Application Submission: | 2025-11-05
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include required semester project reports and the final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  | Estimated Start Date |  | Estimated Completion Date
Initial approval of project by the Uni administration |  | 2024-04-15 |  | 2024-04-15
Formed a team of collaborators with faculty and staff from F & S, Illinois Extension, iSEE, and NRES. |  | 2024-05-25 |  | Ongoing
Complete a 4-week workshop series on pollinator garden design facilitated by staff from Illinois Extension. |  | 2025-09-04 |  | 2025-09-25
Finalize design and seek final approval of the garden from Uni administration. |  | 2025-09-04 |  | 2025-11-21
Notified as recipient of the PTA Youth Engagement Capacity Building grant ($5,000 towards this project) |  | 2025-11-05 |  | 2025-11-05
Present the project to the Architectural Review Committee (ARC) to seek their approval and finalize the memorandum of understanding with F&S. |  | 2025-12-01 |  | 2025-12-12
Submit work order to F & S and site preparation (date range reflecting possible wait time for proper weather conditions) |  | 2025-12-12 |  | 2026-03-15
Submit Progress Report for the Fall of 2025 |  | 2025-12-18 |  | 2025-12-18
Purchase of equipment and plants. |  | 2026-03-02 |  | 2026-04-17
Complete prairie planting alongside collaborators. |  | 2026-04-01 |  | 2026-05-18
Submit Progress Report for the Spring of 2026 |  | 2026-05-14 |  | 2026-05-14
Submit Final Report |  | 2026-10-30 |  | 2026-10-30
ALTERNATE BUDGET #1
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total
Plant Plugs (Pizzo Nursery) |  | 0.5 | 12000 | 6000 | (number and plant species is currently being determined by students designing the garden)
Outdoor Bench Tables |  | 1000 | 5 | 5000
Tool shed |  | 9500 | 1 | 9500
Firepit |  | 275 | 1 | 275
Hose Reel Cart |  | 200 | 1 | 200
Commercial Hose |  | 85 | 2 | 170
B-hyve XD Smart Hose Timer |  | 60 | 2 | 120
Mulch (cubic yard) |  | 27 | 30 | 810
0
0
Equipment & Construction Costs Subtotal |  |  |  | 22075
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
None |  |  |  | 0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
None |  |  |  | 0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
Floral Shovel |  | 28 | 10 | 280
Field Rake |  | 100 | 5 | 500
Bow Rake |  | 30 | 5 | 150
Garden scissors |  | 20 | 10 | 200
Garden Bypass Loppers |  | 35 | 10 | 350
Gloves |  | 10 | 10 | 100
Buckets |  | 4.75 | 6 | 28.5
0
0
0
General Supplies & Other Subtotal |  |  |  | 1608.5
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
Site preparation |  | 1000 | 1 | 1000
F & S Site maintenance (2 years) |  | 2000 | 2 | 4000
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 5000
TOTAL PROJECT BUDGET |  |  |  | 28683.5

## Applic - Alternate Budget 2
SSC Budget and Timeline Form - New Application - Alternate Budget #2
The SSC Budget and Timeline Form - New Application - Alternate Budget #2 is an optional document that can be submitted with the original proposed budget for a new project. Complete this document if you wish to offer the SSC a reduced budget scenario in case they cannot fully fund your entire budget. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. Completion of this form does not guarantee funding. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Uni High Native Prairie Garden
| Alternate Amount Requested from SSC*: | 23899.25 | (<*This field autopopulates based on your budget entries below. Do not edit.)
| Date of This Application Submission: | 2025-11-05
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include required semester project reports and the final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  | Estimated Start Date |  | Estimated Completion Date
Initial approval of project by the Uni administration |  | 2024-04-15 |  | 2024-04-15
Formed a team of collaborators with faculty and staff from F & S, Illinois Extension, iSEE, and NRES. |  | 2024-05-25 |  | Ongoing
Complete a 4-week workshop series on pollinator garden design facilitated by staff from Illinois Extension. |  | 2025-09-04 |  | 2025-09-25
Finalize design and seek final approval of the garden from Uni administration. |  | 2025-09-04 |  | 2025-11-21
Notified as recipient of the PTA Youth Engagement Capacity Building grant ($5,000 towards this project) |  | 2025-11-05 |  | 2025-11-05
Present the project to the Architectural Review Committee (ARC) to seek their approval and finalize the memorandum of understanding with F&S. |  | 2025-12-01 |  | 2025-12-12
Submit work order to F & S and site preparation (date range reflecting possible wait time for proper weather conditions) |  | 2025-12-12 |  | 2026-03-15
Submit Progress Report for the Fall of 2025 |  | 2025-12-18 |  | 2025-12-18
Purchase of equipment and plants. |  | 2026-03-02 |  | 2026-04-17
Complete prairie planting alongside collaborators. |  | 2026-04-01 |  | 2026-05-18
Submit Progress Report for the Spring of 2026 |  | 2026-05-14 |  | 2026-05-14
Submit Final Report |  | 2026-10-30 |  | 2026-10-30
ALTERNATE BUDGET #2
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total
Plant Plugs (Pizzo Nursery) |  | 0.5 | 6000 | 3000
Benches |  | 675 | 5 | 3375
Tool shed |  | 9500 | 1 | 9500
Firepit |  | 275 | 1 | 275
Hose Reel Cart |  | 200 | 1 | 200
Commercial Hose |  | 85 | 2 | 170
B-hyve XD Smart Hose Timer |  | 60 | 2 | 120
Mulch (cubic yard) |  | 27 | 30 | 810
Rain Barrel |  | 170 | 2 | 340
Oscillating Sprinkler |  | 60 | 4 | 240
Equipment & Construction Costs Subtotal |  |  |  | 18030
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
Floral Shovel |  | 28 | 5 | 140
Field Rake |  | 100 | 3 | 300
Bow Rake |  | 30 | 3 | 90
Garden scissors |  | 20 | 5 | 100
Garden Bypass Loppers |  | 35 | 5 | 175
Gloves |  | 10 | 5 | 50
Buckets |  | 4.75 | 3 | 14.25
0
0
0
General Supplies & Other Subtotal |  |  |  | 869.25
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
Site preparation |  | 1000 | 1 | 1000
F & S Site maintenance (2 years) |  | 2000 | 2 | 4000
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 5000
TOTAL PROJECT BUDGET |  |  |  | 23899.25