## Applic - Alternate Budget 1 Fix
SSC Budget and Timeline Form - New Application - Alternate Budget #1
The SSC Budget and Timeline Form - New Application - Alternate Budget #1 is an optional document that can be submitted with the original proposed budget for a new project. Complete this document if you wish to offer the SSC a reduced budget scenario in case they cannot fully fund your entire budget. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. Completion of this form does not guarantee funding. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Illini Union Food Court Lighting Upgrade
| Alternate Amount Requested from SSC*: | 62916.995 | (<*This field autopopulates based on your budget entries below. Do not edit.)
| Date of This Application Submission: | 2025-10-03
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include required semester project reports and the final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  | Estimated Start Date |  | Estimated Completion Date
Demoliotion and Recycling of Existing Fixtures |  | Around December 1st |  | Jan 26th
Installation of New Lighting Fixtures |  | Around December 15th |  | Jan 26th
Installation of New Lighting System |  | Around December 15th |  | Jan26th
Patchwork and Clean Up |  | Around Jan 15th |  | Jan 26th
ALTERNATE BUDGET #1
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total
F1 2X2 Troffer LED Fixture HEW BP-22-LS/8CS-QS-DIM-UNV |  | 65.35 | 67 | 4378.45
F2 2X2 Troffer LED Fixture HEW BP-22-LS/8CS-QS-DIM-UNV LED Fixture |  | 65.35 | 4 | 261.4
F3 6" LED Downlight 6DR-TL-L10/835-DIM-UNV-OW-OF-CS-N-F |  | 209.15 | 75 | 15686.25
F3 6" LED Downlight EM 6" Round Surface LED Downlight Fixture |  | 37.25 | 8 | 298
F4 4' Recessed LED Wallwash Fixture RWG-4-L60/835-S-DIM-UNV Recessed |  | 281.05 | 15 | 4215.75
TAPER Round Drum LED Light Fixture 2662-16-NT-B12-GYL-CC1-35K-CE1-SP |  | 769.45 | 4 | 3077.8
TAPER Round Drum LED Light Fixture 2662-12-NT-B12-GYL-CC1-35K-CE1-SP |  | 616.65 | 6 | 3699.9
NILI NPODMA DX IV |  | 153.4 | 2 | 306.8
nLight NBRG 8 KIT |  | 444.8 | 1 | 444.8
LALT NPP16EFP POWER/RELAY PACK |  | 150.7 | 11 | 1657.7
NPP PCD EFP Phase Dimmer |  | 390.15 | 1 | 390.15
NECY MVOLT ENC |  | 1852 | 1 | 1852
NTS 7IN XX nLight Touch Screen, 7 Inch Screen |  | 1316.65 | 1 | 1316.65
Equipment & Construction Costs Subtotal |  |  |  | 37585.65
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
Industrial Electric Supply Commissioning and Start-Up |  | 833.345 | 1 | 833.345
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 833.345
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
TAPER LIGHTING SPECIAL COATING SET-UP FEE |  | 500 | 1 | 500
Manufacturing, Procurement, and Shipping |  | 23498 | 0 | 23498
Roll off Dumpster |  | 500 | 1 | 500
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 24498
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 0
TOTAL PROJECT BUDGET |  |  |  | 62916.995

## Application - Budget
SSC Budget and Timeline Form - New Application
The SSC Budget and Timeline Form - New Application must be completed and submitted with the SSC Funding Application - Step 1, SSC Funding Application - Step 2 and the SSC Funding Application - Student Led Under $10,00.00. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. *NOTE: The SSC is not able to fund every project in full for which we receive an application. If you wish to also present alternate, lower budget scenarios to guide the SSC in making decisions in case we cannot fully fund your project, you may complete the additional tabs in this document labeled "Applic-Alternate Budget 1" and "Applic-Alternate Budget 2". If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Illini Union Food Court Lighting Upgrade
| Amount Requested from SSC*: | 231818.395 | (<*This field autopopulates based on your budget entries below. Do not edit.)
| Date of This Application Submission: | 2025-10-03
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  | Estimated Start Date |  | Estimated Completion Date
Demoliotion and Recycling of Existing Fixtures |  | Around December 1st |  | Jan 26th
Installation of New Lighting Fixtures |  | Around December 15th |  | Jan 26th
Installation of New Lighting System |  | Around December 15th |  | Jan26th
Patchwork and Clean Up |  | Around Jan 15th |  | Jan 26th
BUDGET
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total
F1 2X2 Troffer LED Fixture HEW BP-22-LS/8CS-QS-DIM-UNV |  | 65.35 | 67 | 4378.45
F2 2X2 Troffer LED Fixture HEW BP-22-LS/8CS-QS-DIM-UNV LED Fixture |  | 65.35 | 4 | 261.4
F3 6" LED Downlight 6DR-TL-L10/835-DIM-UNV-OW-OF-CS-N-F |  | 209.15 | 75 | 15686.25
F3 6" LED Downlight EM 6" Round Surface LED Downlight Fixture |  | 37.25 | 8 | 298
F4 4' Recessed LED Wallwash Fixture RWG-4-L60/835-S-DIM-UNV Recessed |  | 281.05 | 15 | 4215.75
TAPER Round Drum LED Light Fixture 2662-16-NT-B12-GYL-CC1-35K-CE1-SP |  | 769.45 | 4 | 3077.8
TAPER Round Drum LED Light Fixture 2662-12-NT-B12-GYL-CC1-35K-CE1-SP |  | 616.65 | 6 | 3699.9
NILI NPODMA DX IV |  | 153.4 | 2 | 306.8
nLight NBRG 8 KIT |  | 444.8 | 1 | 444.8
LALT NPP16EFP POWER/RELAY PACK |  | 150.7 | 11 | 1657.7
NPP PCD EFP Phase Dimmer |  | 390.15 | 1 | 390.15
NECY MVOLT ENC |  | 1852 | 1 | 1852
NTS 7IN XX nLight Touch Screen, 7 Inch Screen |  | 1316.65 | 1 | 1316.65
Equipment & Construction Costs Subtotal |  |  |  | 37585.65
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
Industrial Electric Supply Commissioning and Start-Up |  | 833.345 | 1 | 833.345
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 833.345
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
Roll off Dumpster |  | 500 | 1 | 500
TAPER LIGHTING SPECIAL COATING SET-UP FEE |  | 500 | 1 | 500
Manufacturing, Procurement, and Shipping |  | 23498 | 1 | 23498
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 24498
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
Total Estimated Construction and Labor |  | 128840.2 | 1 | 128840.2
10% Contingency (Covers unexpected costs and prevents us from being charged in excess of contingency) |  | 21074.4 | 1 | 21074.4
Carpenters, Transportation, Painters, and Time |  | 18986.8 | 1 | 18986.8
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 168901.4
TOTAL PROJECT BUDGET |  |  |  | 231818.395

## Applic - Alternate Budget 2 Lab
SSC Budget and Timeline Form - New Application - Alternate Budget #2
The SSC Budget and Timeline Form - New Application - Alternate Budget #2 is an optional document that can be submitted with the original proposed budget for a new project. Complete this document if you wish to offer the SSC a reduced budget scenario in case they cannot fully fund your entire budget. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. Completion of this form does not guarantee funding. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Illini Union Food Court Lighting Upgrade
| Alternate Amount Requested from SSC*: | 168901.4 | (<*This field autopopulates based on your budget entries below. Do not edit.)
| Date of This Application Submission: | 2025-10-03
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include required semester project reports and the final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  | Estimated Start Date |  | Estimated Completion Date
Demoliotion and Recycling of Existing Fixtures |  | Around December 1st |  | Jan 26th
Installation of New Lighting Fixtures |  | Around December 15th |  | Jan 26th
Installation of New Lighting System |  | Around December 15th |  | Jan26th
Patchwork and Clean Up |  | Around Jan 15th |  | Jan 26th
ALTERNATE BUDGET #2
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 0
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
Carpenters, Transportation, Painters, and Time |  | 18986.8 |  | 18986.8
10% Contingency (Covers unexpected costs and prevents us from being charged in excess of contingency) |  | 21074.4 | 1 | 21074.4
Total Estimated Construction and Labor |  | 128840.2 | 1 | 128840.2
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 168901.4
TOTAL PROJECT BUDGET |  |  |  | 168901.4

## Applic - Alternate Budget 3 Sou
SSC Budget and Timeline Form - New Application - Alternate Budget #2
The SSC Budget and Timeline Form - New Application - Alternate Budget #2 is an optional document that can be submitted with the original proposed budget for a new project. Complete this document if you wish to offer the SSC a reduced budget scenario in case they cannot fully fund your entire budget. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. Completion of this form does not guarantee funding. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Illini Union Food Court Lighting Upgrade
| Alternate Amount Requested from SSC*: | 188019.4 | (<*This field autopopulates based on your budget entries below. Do not edit.)
| Date of This Application Submission: | 2025-10-03
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include required semester project reports and the final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  | Estimated Start Date |  | Estimated Completion Date
Demoliotion and Recycling of Existing Fixtures |  | Around December 1st |  | Jan 26th
Installation of New Lighting Fixtures |  | Around December 15th |  | Jan 26th
Installation of New Lighting System |  | Around December 15th |  | Jan26th
Patchwork and Clean Up |  | Around Jan 15th |  | Jan 26th
ALTERNATE BUDGET #2
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total
F1 2X2 Troffer LED Fixture HEW BP-22-LS/8CS-QS-DIM-UNV |  | 65.35 | 56 | 3659.6
F2 2X2 Troffer LED Fixture HEW BP-22-LS/8CS-QS-DIM-UNV LED Fixture |  | 65.35 | 0 | 0
F3 6" LED Downlight 6DR-TL-L10/835-DIM-UNV-OW-OF-CS-N-F |  | 209.15 | 71 | 14849.65
F3 6" LED Downlight EM 6" Round Surface LED Downlight Fixture |  | 37.25 | 6 | 223.5
| F4 4' Recessed LED Wallwash Fixture RWG-4-L60/835-S-DIM-UNV Recessed | 281.05 | 15 | 4215.75
| TAPER Round Drum LED Light Fixture 2662-16-NT-B12-GYL-CC1-35K-CE1-SP | 769.45 | 4 | 3077.8
TAPER Round Drum LED Light Fixture 2662-16-NT-B12-GYL-CC1-35K-CE1-SP |  | 616.65 | 6 | 3699.9
NILI NPODMA DX IV |  | 153.4 | 2 | 306.8
nLight NBRG 8 KIT |  | 444.8 | 1 | 444.8
LALT NPP16EFP POWER/RELAY PACK |  | 150.7 | 11 | 1657.7
| NPP PCD EFP Phase Dimmer | 390.15 | 1 | 390.15
| NECY MVOLT ENC | 1852 | 1 | 1852
NTS 7IN XX nLight Touch Screen, 7 Inch Screen |  | 1316.65 | 1 | 1316.65
Equipment & Construction Costs Subtotal |  |  |  | 35694.3
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
Industrial Electric Supply Commissioning and Start-Up |  | 833.35 | 1 | 833.35
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 833.35
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
Roll off Dumpster |  | 1 | 500 | 500
TAPER LIGHTING SPECIAL COATING SET-UP FEE |  | 1 | 500 | 500
Manufacturing, Procurement, and Shipping |  | 1 | 18748.35 | 18748.35
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 19748.35
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
Carpenters, Transportation, Painters, and Time |  | 16586.8 | 1 | 16586.8
10% Contingency (Covers unexpected costs and prevents us from being charged in excess of contingency) |  | 17696.4 | 1 | 17696.4
Total Estimated Construction and Labor |  | 97460.2 | 1 | 97460.2
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 131743.4
TOTAL PROJECT BUDGET |  |  |  | 188019.4

## Applic - Alternate Budget 4 nor
SSC Budget and Timeline Form - New Application - Alternate Budget #2
The SSC Budget and Timeline Form - New Application - Alternate Budget #2 is an optional document that can be submitted with the original proposed budget for a new project. Complete this document if you wish to offer the SSC a reduced budget scenario in case they cannot fully fund your entire budget. This form requires a list of all project timelines and milestones and a detailed list of planned expenditures by category. Completion of this form does not guarantee funding. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | Illini Union Food Court Lighting Upgrade
| Alternate Amount Requested from SSC*: | 43799 | (<*This field autopopulates based on your budget entries below. Do not edit.)
| Date of This Application Submission: | 2025-10-03
SCOPE & SCHEDULE
What is the plan for project implementation? Describe the key steps of the project including the estimated start and completion dates. Include required semester project reports and the final project report. Be as detailed as possible so that the SSC can fully evaluate the merit of this application. Insert additional rows if necessary.
Task |  | Estimated Start Date |  | Estimated Completion Date
Demoliotion and Recycling of Existing Fixtures |  | Around December 1st |  | Jan 26th
Installation of New Lighting Fixtures |  | Around December 15th |  | Jan 26th
Installation of New Lighting System |  | Around December 15th |  | Jan26th
Patchwork and Clean Up |  | Around Jan 15th |  | Jan 26th
ALTERNATE BUDGET #2
List all budget items for which funding is being requested under the appropriate category. Include cost and total amount for each item. Be as detailed as possible. Insert additional rows if necessary.
Equipment & Construction Costs
Item |  | Cost Per Item | Quantity | Total
F1 2X2 Troffer LED Fixture HEW BP-22-LS/8CS-QS-DIM-UNV |  | 65.35 | 11 | 718.85
F2 2X2 Troffer LED Fixture HEW BP-22-LS/8CS-QS-DIM-UNV LED Fixture |  | 65.35 | 4 | 261.4
F3 6" LED Downlight 6DR-TL-L10/835-DIM-UNV-OW-OF-CS-N-F |  | 209.15 | 4 | 836.6
F3 6" LED Downlight EM 6" Round Surface LED Downlight Fixture |  | 37.25 | 2 | 74.5
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 1891.35
Publicity & Communication
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  | Cost Per Item | Quantity | Total
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  | Cost Per Item | Quantity | Total
Retrofit F7 lights North |  | 169.99 | 11 | 1869.89
Retrofit F7A lights North |  | 179.985 | 16 | 2879.76
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 4749.65
Illinois Facilities and Services (F&S) Division Budget Items
Item |  | Cost Per Item | Quantity | Total
Carpenters, Transportation, Painters, and Time |  | 2400 | 1 | 2400
10% Contingency (Covers unexpected costs and prevents us from being charged in excess of contingency) |  | 3378 | 1 | 3378
Total Estimated Construction and Labor |  | 31380 | 1 | 31380
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 37158
TOTAL PROJECT BUDGET |  |  |  | 43799