## Initial Budget
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Women's Resources Center
Total Amount Requested from SSC: | 19990
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
recruit and review applications for a Summer/Fall 2023 Ecofeminism Summit intern | May 2023 (4 weeks) |  | 2023-06-01
Review feedback from the Spring 2022 and Spring 2023 Ecofeminism Summits | June 2023 (2 weeks) |  | 2023-06-14
Identify potential campus partners and form a fall 2023 planning committee | June 2023 (2 weeks) |  | 2023-06-14
Host bi-weekly planning committee meetings to determine learning objectives, identify speakers and activities, and develop assessment tool | June - July 2023 (6 weeks) |  | 2023-07-31
Invite identified speakers and confirm dates | July - August 2023 (4 weeks) |  | 2023-08-14
Finalize Summit Schedule and develop marketing | 2023-08-01 |  | 2023-08-14
Promote Summit at events and on digital signage | September 11 - September 29 (3 weeks) |  | 2023-09-29
Host summit events | September 18 - September 29 (2 weeks) |  | 2023-09-29
Evaluate Summit outcomes | October 2023 (4 weeks) |  | 2023-10-31
Submit final report | November 2023 (2 weeks) |  | 2023-11-14
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
Digital Signage (Housing, $40/week) | 40 | 1 | 40
Digital Bulletin Boards (Illini Union, $75/week) | 75 | 2 | 150
Digital Bulletin Boards (Campus Rec, $75/week) | 75 | 2 | 150
0
0
0
0
0
0
0
|  | Subtotal | 340
Personnel & Wages
Ecofeminism Summit Intern Wages ($15/hr, 10 hrs/wk for 31 weeks) | 15 | 310 | 4650
0
0
0
0
0
0
0
0
0
|  | Subtotal | 4650
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Speaker Honorarium | 5000 | 1 | 5000
Speaker Honorarium | 10000 | 1 | 10000
0
0
0
0
0
0
0
0
|  | Subtotal | 15000
|  | TOTAL BUDGET | 19990
End of Application

## Revised Budget
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact SSC at Sustainability-Committee@illinois.edu.
GENERAL INFORMATION
Project Title: | Women's Resources Center
Total Amount Requested from SSC: | 19990
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
recruit and review applications for a Summer/Fall 2023 Ecofeminism Summit intern | May 2023 (4 weeks) |  | 2023-06-01
Review feedback from the Spring 2022 and Spring 2023 Ecofeminism Summits | June 2023 (2 weeks) |  | 2023-06-14
Identify potential campus partners and form a fall 2023 planning committee | June 2023 (2 weeks) |  | 2023-06-14
Host bi-weekly planning committee meetings to determine learning objectives, identify speakers and activities, and develop assessment tool | June - July 2023 (6 weeks) |  | 2023-07-31
Invite identified speakers and confirm dates | July - August 2023 (4 weeks) |  | 2023-08-14
Finalize Summit Schedule and develop marketing | 2023-08-01 |  | 2023-08-14
Promote Summit at events and on digital signage | September 11 - September 29 (3 weeks) |  | 2023-09-29
Host summit events | September 18 - September 29 (2 weeks) |  | 2023-09-29
Evaluate Summit outcomes | October 2023 (4 weeks) |  | 2023-10-31
Submit final report | November 2023 (2 weeks) |  | 2023-11-14
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Publicity & Communication
Digital Signage (Housing, $40/week) | 40 | 1 | 40
Digital Bulletin Boards (Illini Union, $75/week) | 75 | 2 | 150
Digital Bulletin Boards (Campus Rec, $75/week) | 75 | 2 | 150
0
0
0
0
0
0
0
|  | Subtotal | 340
Personnel & Wages
Summer Ecofeminism Summit Intern Wages ($14/hr, 10 hrs/wk for 6.5 weeks) | 15 | 65 | 975
Summer Ecofeminism Summit Intern Wages ($14/hr, 10 hrs/wk for 16 weeks) | 7.5 | 160 | 1200
0
0
0
0
0
0
0
0
|  | Subtotal | 2175
Project Budget per F&S
0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
Speaker Honorarium (Niha) | 2500 | 1 | 2500
Speaker Honorarium (Leah Thomas) | 10000 | 1 | 10000
Hotel for two nights (Leah Thomas) | 145.77 | 2 | 291.54
Books for Braiding Sweetgrass Book Club | 13.25 | 25 | 331.25
Prizes for Ecofeminism Trivia Night | 15 | 12 | 180
Giveaways (Reusable Bags) | 4 | 250 | 1000
Giveaways (Ecofeminism Stickers) | 0.4 | 500 | 200
0
0
0
|  | Subtotal | 14502.79
|  | TOTAL BUDGET | 17017.79
End of Application