## Final Project Report
SSC Budget and Timeline Form - Final Project Report
The SSC Budget and Timeline Form - Final Project Report must be completed upon completion of a project OR upon expiration of an award, whichever comes first. This form requires a complete list of updated project timelines and milestones for the project and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | UIUC Rainwater Management Plan (changed to Program)
| Original Award Date (or Semester/Year)*: | 2023-05-03 | <*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): | 200000
| Total Expenses This Period**: | 0 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: | 0 | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Date of This Application Submission: | 2025-04-28
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the work you accomplished on the entire project. Include start and end dates and % complete). Be as detailed as possible so that the SSC can fully evaluate this project. Insert additional rows if necessary.
Task |  |  | Start Date | End Date (or estimated) | % Complete
Begin Capital Project, gain project approval and contract with a retainer engineer with Facilities & Services (F&S) |  |  | 2023-10-30 | 2024-02-29 | 100%
kick off meeting |  |  | 2024-03-04 | 2024-03-04 | 100%
Engineer to gather data and discuss issues with stakeholders |  |  | 2024-03-04 | 2024-06-30 | 100%
Engineer prepare Draft program and submit for owner review |  |  | 2024-06-30 | 2024-11-14 | 100%
Owner review Draft program |  |  | 2024-11-14 | 2024-12-17 | 100%
Three facility manager meetings (11/8, 12, 19/2024) |  |  | 2024-11-08 | 2024-11-19 | 100%
Engineer to respond to comments, prepare Pre-Final program and submit for review |  |  | 2024-12-17 | 2025-01-21 | 100%
Owner review Pre-Final program |  |  | 2025-01-21 | 2025-02-14 | 100%
Engineer to respond to comments, prepare Final program and submit for review |  |  | 2025-02-14 | 2025-03-10 | 100%
Owner review Final program |  |  | 2025-03-10 | 2025-03-17 | 100%
Public Forum prep, advertisment and presentaion |  |  | 2025-03-07 | 2025-04-02 | 100%
Engineer to respond to comments, prepare Final For Print program and submit. |  |  | 2025-04-02 | 2025-04-21 | 100%
Owner review final. Project complete. |  |  | 2025-04-21 | 2025-04-28 | 100%
EXPENSES
List all expenditures from this award made since the last semester report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  |  | Total Spent
NA |  |  |  | 0
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 0
Publicity & Communication
Item |  |  |  | Total Spent
Facilities & Services Customer Relations & Communications campus publicity/free |  |  |  | 0
Consultant provided a public forum on the final report/included in consultant fee |  |  |  | 0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 0
General Supplies & Other
Item |  |  |  | Total Spent
NA |  |  |  | 0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  | Total Spent
Consultant fee (project is at substantial completion, final numbers to be determined at close out) |  |  |  | 176930
F&S Standards Review costs (project is at substantial completion, final numbers to be determined at close out) |  |  |  | 5000
Project Management fees (project is at substantial completion, final numbers to be determined at close out) |  |  |  | 10000
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 191930
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  | 191930