## Semester_Project_Report
SSC Budget and Timeline Form - Semester Project Report
The SSC Budget and Timeline Form - Semester Project Report must be completed and submitted every semester regardless of the original application type. This form requires a list of updated project timelines and milestones and a detailed list of expenditures by category since the last submitted Semester Progress Report. If you have questions, please email the SSC at Sustainability-Committee@illinois.edu.
GENERAL PROJECT INFORMATION
| Project Title: | UIUC Rainwater Management Plan
| Original Award Date (or Semester/Year)*: | 2023-05-03 | (<*Awards are valid for 2 years from award date unless there is an approved Scope Change on file.)
| Total Amount of Award (Including Any Budget Increases Associated with Approved Scope Changes): | 200000
| Total Expenses This Period**: | 14924.02 | <**This field autopopulates based on your expense entries below. Do not edit.
| Remaining Unspent Funds in Award***: | 185075.98 | <***NOTE: The SSC will rescind remaining funds from completed and expired awards.
| Expected Date of Project Completion: | 2025-03-01
| Date of This Application Submission: | 2024-12-04
SCOPE & SCHEDULE
Referencing the project's original tasks and schedule (or revised tasks and/or schedule via approved Scope Change), detail the progress you have made on the project since your last semester report. Include start and end dates and % complete). Include the required semester project reports and the required final project report. Be as detailed as possible so that the SSC can fully evaluate the progress of this project. Insert additional rows if necessary.
Task |  |  | Start Date | End Date (or estimated) | % Complete
Owner review the engineer provided draft master plan |  |  | 2024-11-14 | 2024-12-17 | 50%
Engineer to respond to comments, prepare Pre-Final master plan and submit for review. |  |  | 2024-12-17 | 2025-01-06 | 0%
Owner provide comments on pre-final master plan |  |  | 2025-01-06 | 2025-02-01 | 0%
Engineer to respond to comments, prepare Final master plan and submit. |  |  | 2025-02-01 | 2025-02-15 | 0%
Finalize project & Public Forum |  |  | 2025-02-15 | 2025-03-01 | 0%
EXPENSES
List all expenditures from this award made since the last submitted semester project report. You can combine recurring similar expenses into one summed entry. Note that your expenses should reflect those that were approved in the original budget (or approved Scope Change). Insert additional rows if necessary.
Equipment & Construction Costs
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Equipment & Construction Costs Subtotal |  |  |  | 0
Publicity & Communication
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
Publicity & Communication Subtotal |  |  |  | 0
Personnel & Wages
Item |  |  |  | Total Spent
consultant fees |  |  |  | 10925
0
0
0
0
0
0
0
0
0
Personnel & Wages Subtotal |  |  |  | 10925
General Supplies & Other
Item |  |  |  | Total Spent
0
0
0
0
0
0
0
0
0
0
General Supplies & Other Subtotal |  |  |  | 0
Illinois Facilities and Services (F&S) Division Budget Items
Item |  |  |  | Total Spent
Project Management |  |  |  | 3999.02
0
0
0
0
0
0
0
0
0
Illinois Facilities and Services (F&S) Division Budget Subtotal |  |  |  | 3999.02
TOTAL EXPENSES FOR CURRENT PERIOD |  |  |  | 14924.02